## Instructions
Piping (Home Office) Labor Hour Estimating
Warning
This Excel Worksheet or Workbook "Tool" is locked and password protected. The user may only enter date in the "yellow" cells. Other cells on this "Tool" includes locked "cells" that contain complex math formulas. Care should be taken to learn where these cells are and if the spreadsheet is ever unlocked that the cells with the formulas are not disturbed. Disturbing or altering these cells may render the "Tool" unable to function properly.
Introduction
This WorkBook "Tool" is part of a suite of 6 "Tools" that are intended to aid the Piping Engineering Lead (Senior Supervisor or whatever he or she is called) who has the responsibility to make estimates, schedules, control the work, the hours, report the progress and prepare & files the Final Job Report. These "Tools" are: (1) Piping Engineering & Design Scope of Work, (3) Piping Labor Hour Estimating Forms, (3) Piping Control Level Schedule, (4) Physical Percent Complete Status Report, (5) Design Change Notice and (6) "Janus" Historical Data Log. These 5 WorkBook Tools are intended to be used as a "Set" and will bring value to your effort only if you in fact use all of them.
Authors note: The information used in this example Labor Hour Estimate is pure fiction created by the author and any resemblance to real persons, projects, companies or places is coincidental.
# 1
Study these instructions and all three of the WorkSheets of this WorkBook. If you have any questions about anything here please contact me via E-mail (jopennock@netscape.net) and I will help you.
# 2
Make a Copy of the complete WorkBook and save it to your Project data base.
# 3
The Prerequisite for the use of this tool is a completed and approved Scope of Work (SOW). Without an approved SOW it is not possible to develop a Labor Hour Estimate because there is no definition of what is to be done.
# 4
Start with the "Estimate Detail" sheet and enter the Project Number in the cell provided in the upper left corner. This number (and others) will be transferred to the Estimate Summary sheet automatically
# 5
Fill in the quantity of deliverables and activities. Use your "Approved" SOW for all the activities and deliverables. Start with the "Default" hours and adjust up or down depending on the complexity that is expected.
# 6
You can fill out almost the whole Estimate by only entering a value in the "Quantity" column. You do not need to enter a value in the "Hours" column. The program automatinally uses the "Default" value.
# 7
If you are not comfortable with the results using the "Default" value then you can enter a greater or lesser value in the "Hours" column.
# 8
When you have finished entering all the required data on the Estimate Detail sheet, look at the Summary sheet and finish the header information (yellow cells). You will notice that all the Totals and Percantages have been transferred for you.
# 9
Your next step will be the creation of your CLS (Control Level Schedule). To prepare for that collect the Operation Number/Activity Code totals (example: the 251 A total, thew 251 B total, etc).
#10
At the end of the project collect the "actual" numbers for the number of deliverables and the hours it took to do the work. This historical data will help you with the estimate for your next project.

## Time Charge Codes
Piping Group Time Charge Codes
Activity Grouping | Acitivity Code | Piping Sub-Group Operation Number & Name (*)
|  | 250 | 251 | 252 | 253 | 254
|  | PEL | PME | PDG | PMC | PSE
Supervision | A | Work Assignment, Planning, Status Report Meetings w/ Department, Project & Client, Emp.. Perform. Reviews, Technical Direction, P&ID Reviews | Work Assignment, Work review, Meetings, Status Reports, Emp.. Perform. Review, P&ID Reviews | Work Assignment, Work review, Meetings, Status Reports, Emp.. Perform. Review, P&ID Reviews | Work Assignment, Work review, Meetings, Status Reports, Emp.. Perform. Review, P&ID Reviews | Work Assignment, Work review, Meetings, Status Reports, Emp.. Perform. Review, P&ID Reviews
Project Design Basis | B | SOW, Labor Hour Estimate, Control Level Schedule, Collect, Review and Disseminate Client Criteria, Coordinate Vendor SQ CK, Field Trips | Specifications, Standards, Develop CCC, Vendor Data SQ CK | Specifications, Standards, Plot Plan Developm't, Vendor Data SQ CK, Heat Tracing Criteria, Field Trips | Establish Mat'l Take-Off Data Base, Define Material "Bump" Criteria, | Specifications, Standards, Define Pipe Stress Analysis Criteria, Pre-Eng. Pipe Supports Vendor Data SQ CK
Preliminary Design | C |  |  | Transpositions, Vessel Orientations, Model Index, Drawing Index, Layout Studies, | Preliminary MTO & RFQ
Detailed Design | D | Model Reviews | SP Item Activities, Model Reviews, | 2D CADD, 3D CADD, Manual Drawings, Revise Exist. Dwgs.,Model Reviews, | Intermediate MTO and POR, Model Reviews | Model Reviews, Pipe Stress Analysis, Hanger Data Sheets, Joint Data Sheets, Review & Sign Isometrics
Deliverables | E | Construction Work Packages (CWP) | Line List | Manual Isometrics, CADD Isometrics, Piping Plans, Piping Sections, Isometric Index, Tie-In Index, Tie-In List, Tie-In Isos., Heat Tracing Isometrics, Heat Tracing Index, Demo Dwg's, | Final MTO, PO Supplements, Shortage Reports, Overage Reports, | Expansion Joint Dwgs, Spring Hanger Dwgs, Strut Dwgs.
Services | F |  |  | CADD Coordinator
(*) Definition of Piping Sub-Group Numbers & Names
250 - PEL = Piping Engineering Lead (See Company Job Description)
251 - PME = Piping Material Engineer (See Company Job Description)
252 - PDG = Piping Design Group (See Company Job Description)
253 - PMC = Piping Material Control (See Company Job Description)
254 - PSE = Piping Stress Engineering (See Company Job Description)

## Estimate Summary Example
PIPING ENGINEERING AND DESIGN __ SUMMARY OF HOME OFFICE LABOR AND COST ESTIMATE & FINAL REPORT
PROJECT NAME: | Temple Refinery Upgrade | PROJECT MANAGER: |  | Al Demming
CLIENT: | ACME Products, LLC | PREPARED BY (LPE): |  | A. R. Tennyson |  |  | EST. LINE COUNT: |  | 900
LOCATION: | Anywhere, | APPROVED BY: |  | A. G. Patterson |  |  | EQUIV. ISO. COUNT: |  | 2160
PROJECT NO.: | 2011-106 | FINAL REPORT BY: |  |  |  |  | EST. TIC: ($MM) |  | $200MM
PLANT TYPE: | Refinery |  | REV.: | 0 | 1
CONTRACT TYPE : | EPCM | (EPC, EPCM, etc.) | DATE: | 2011-08-01 |  |  | FINAL ISO COUNT : |  | 0
PIPING ENGINEERING |  | DISCIPLINE ESTIMATE |  |  |  | APPV'D BUDGET |  | FINAL REPORT
OPER. No. | GROUP | ESTIMATED LABOR HOURS | % OF TOTAL | ESTIMATED COMPUTER EXPENSES $ | ESTIMATED TRAVEL & LODGING EXPENSES $ | BUDGET LABOR HOURS | % OF TOTAL | ACTUAL LABOR HOURS | % OF TOTAL
251 | PIPE MATERIAL ENGR. | 772.2 | 2.791% |  | 500 |  |  | 0
252 | PIPING DESIGN | 15339.5 | 55.45% |  | 6000 |  |  | 0
253 | PIPE MATERIAL CONTROL | 3800.5 | 13.74% |  |  |  |  | 0
254 | PIPE STRESS ENGR. | 5624 | 20.33% |  | 1000 |  |  | 0
SUB TOTAL TECHNICAL LABOR HRS = |  | 25536.2 |  | 0 | 7500 | 0 |  | 0
250 | LPE, DEPT. & STAFF | 2127.4 | 7.69% |  |  |  |  | 0
ALL | TOTAL LABOR HOURS | 27663.6 | 100 % |  |  | 0 | 100 % | 0 | 100 %
REMARKS: |  | HRS/ISO= | 12.81 |  |  | HRS/ISO= | #VALUE! | HRS/ISO = | #VALUE!

## Estimate Detail Example
PIPING ENGINEERING & DESIGN HOME OFFICE LABOR, EXPENSE ESTIMATE DETAIL | [10 empty] | PIPING ENGINEERING & DESIGN FINAL REPORT DETAIL
|  |  |  | PLEASE NOTE Only the yellow boxes are for data entry | [9 empty] | The area below is to be used only at the end of the project to record the historical actual data.
PROJECT NO.
| 2011-106 | [9 empty] | 2011-106
251. . . . P I P I N G M A T E R I A L E N G I N E E R I N G | [6 empty] | ESTIMATE |  | NOTES: | [5 empty] | FINAL
| SPECIFICATIONS | SPEC NO. |  | QUANTITY | HOURS | DEFAULT | LABOR HRS | TOTAL LABOR HRS | [5 empty] | QUANTITY | LABOR HRS | TOTAL LABOR HRS
B | PIPING MAT'L LINE CLASS NOTES & DATA | Review Existing |  | 1 | 4 | 20 | 4
B | INDIVIDUAL LINE CLASS SPECS | Review Existing |  | 22 | 5 | 20 | 110
B | PURCHASE (PIPE, VALVES, FITTINGS, ETC.) | 52001 to 52010 |  | 10 |  | 5 | 50
B | TESTING, CLEANING, PASSIVATING |  |  | 0 |  | 20 | 0
B | SP ITEM - SPEC, LIST, & DATASHEETS | 52024 |  | 20 | 4 | 8 | 80
B | ISULATING,PAINTING,COATING,LINING |  |  | 0 |  | 20 | 0
B | WELDING / NDE |  |  | 0 |  | 20 | 0
| TOTAL NUMBER OF SPECIFICATIONS AND HOURS |  |  |  | 53 |  | 244 | [7 empty] | 0
| ACTIVITIES | [5 empty] | LABOR HRS | [7 empty] | LABOR HRS
B | PROJECT COMMODITY CATLAOG | [5 empty] | 8 | [5 empty] | ACTUAL.
E | LINE LIST / INDEX - DEVELOP & MAINTAIN |  | EST. LINE COUNT |  | 900 | 0.5 | 450 | [5 empty] | LINE No. =
| SUB-TOTAL ACTIVITY MAN HOURS | [5 empty] | 458
A | SUPERVISION |  | 10%= | 70.2 | AJUSTMENT |  | 70.2
| 252--PIPING MATERIAL ENGINEERING TOTALS - HRS | [6 empty] | 772.2 | 2.791% | [6 empty] | 0
2011-106 | [10 empty] | 2011-106
252 . . . . P I P I N G D E S I G N | [6 empty] | ESTIMATE | [6 empty] | FINAL
| ACTIVITY |  |  | NUMBER | HOURS | [6 empty] | SCALE | NUMBER | AVG. HOURS
| DRAWINGS/DOCUMENTS | SCALE | SIZE | OF | PER | DEFAULT |  | TOTAL LABOR HRS |  |  | SIZE | OF | OF | PER | LABOR | TOTAL LABOR HRS
| ( DWG. SIZE= A - B - C - D - E ) | (OPTIONAL) | (OPTIONAL) | ITEMS | ITEM | HRS | LABOR HRS |  |  |  |  | DRAWINGS | DRAWINGS | DRAWING | HRS
C | TRANSPOSITION LAYOUTS (NON CAD) |  |  | 1 | 40 | 100 | 40 | [6 empty] | #DIV/0!
C | LAYOUTS, STUDIES, VESSEL ORIENTATIONS |  |  | 20 | 20 | 40 | 400 | [6 empty] | #DIV/0!
C | LOCATION CONTROL PLANS (LCP) |  |  | 3 | 40 | 120 | 120 | [6 empty] | #DIV/0!
C | PLOT PLANS (SITE AND/OR UNIT) |  |  | 3 | 80 | 100 | 240 | [6 empty] | #DIV/0!
C | PIPING INDEX ( PLANS, MODEL, TIE-IN ) |  |  | 2 |  | 20 | 40 | [6 empty] | #DIV/0!
B | DRAWING /VENDOR PRINT SQ. CK. | VARIOUS | VARIOUS | 200 |  | 1 | 200 | [6 empty] | #DIV/0!
D | PIPING PLAN DRAWINGS ( 2D/MANUAL) |  |  | 0 |  | 141 | 0 | [6 empty] | #DIV/0!
D | 3D MODELING - EQUIPMENT |  |  | 250 |  | 6 | 1500 | [6 empty] | #DIV/0!
D | 3D MODELING - PIPE LINES |  |  | 710 |  | 4 | 2840 | [6 empty] | #DIV/0!
B | PIPING STANDARD & DETAIL DRAWINGS |  |  | 0 |  | 40 | 0
E | HEAT TRACE DRAWINGS (PIPING ONLY) |  |  | 0 |  | 4.25 | 0
E | DEMOLITION DRAWINGS ( NON-CAD) |  |  | 0 |  | 15 | 0
E | ISOMETRICS (NEW LINES & TIE-INS) | N/A |  | 300 |  | 8.25 | 2475
E | PIPING PLAN DRAWINGS (REV EXIST'G) |  |  | 60 | 20 | 40 | 1200
E | PIPING PLAN - AS-BUILTS * |  |  | 0 |  | 20 | 0
E | EXTRACT PLAN DRAWINGS - 3D |  |  | 25 | 10 | 20 | 250
E | EXTRACT ISOMETRICS - 3D |  |  | 1800 |  | 1 | 1800
| SUB-TOTAL DRAWING QUANTITIES AND LABOR HOURS |  |  | 3374 |  |  | 11105 | [5 empty] | 0 | #DIV/0! | 0
| SPECIFICATIONS | SPEC NO. |  | QUANTITY | HRS. PER. | DEFAULT | HRS |  | NOTES: |  |  |  |  | QUANTITY | HRS
B | DESIGN, LAYOUT & DRAWING |  |  | 0 |  | 10 | 0
B | SHOP FABRICATION | 51025 |  | 1 |  | 10 | 10
B | FIELD FABRICATION | 51026 |  | 1 |  | 10 | 10
B | TIE INS | 51045 |  | 1 |  | 10 | 10
B | GEOGRAPHIC COLOR CODE |  |  | 0 |  | 10 | 0
B | HEAT TRACING |  |  | 0 |  | 10 | 0
| SUB-TOTAL NUMBER OF SPECIFICATIONS AND LABOR HOURS | [5 empty] | 30 | [6 empty] | 0 | 0
| ACTIVITY |  |  | QUANTITY | HRS. PER. | DEFAULT | HRS | [6 empty] | QUANTITY | HRS
B | DESIGNER FIELD TRIPS | DAYS / HOURS |  | 0 |  | 8 | 0
E | TIE IN LIST | No TIE-INS/ HRS PER |  | 30 |  | 1 | 30
F | CAD COORDINATOR | WEEKS / HOURS |  | 17 |  | 40 | 680
E | ISOMETRIC DRAWING LIST/INDEX | ISOMETRIC COUNT | = | 2100 |  | 1 | 2100
| SUB-TOTAL ACTIVITY LABOR HOURS | [5 empty] | 2810 | [7 empty] | 0
A | SUPERVISION |  | 10%= | 1394.5 | AJUSTMENT= |  | 1394.5
| 251 - PIPING DESIGN TOTALS - DWGS, SPECS, LABOR HOURS | [6 empty] | 15339.5 | 55.45% | [6 empty] | 0
2011-106 | [10 empty] | 2011-106
253 . . . . P I P I N G M A T E R I A L C O N T R O L | [6 empty] | ESTIMATE |  | NOTES: | [5 empty] | FINAL
| ACTIVITIES |  |  | QUANTITY | HRS. PER. | DEFAULT | HRS | TOTAL LABOR HRS | [5 empty] | QUANTITY | LABOR HRS | TOTAL LABOR HRS
B | MATERIAL MANAGEMENT CRITERIA, P&ID REVIEW |  |  | 60 |  | 3 | 180
C | MAT'L TAKEOFF (PRELIM) & RFQ | PER EQIV. ISO |  | 2100 |  | 0.5 | 1050
D | MAT'L TAKEOFF (INTERMEDIATE) & PO | PER EQIV. ISO |  | 2100 | 0.5 | 1 | 1050
E | MAT'L TAKEOFF (FINAL,MANUAL) & SUPPL. | PER ISO |  | 550 | 0.5 | 1 | 275
E | MAT'L TAKEOFF (FINAL, DOWNLOAD) & SUPPL. | PER ISO |  | 1800 |  | 0.5 | 900
E | MATERIAL OVERAGE?SHORTAGE REPORTS. | PER RFQ/PO, ETC |  | 0 |  | 80 | 0
| SUB-TOTAL ACTIVITY MAN HOURS | [5 empty] | 3455 | [7 empty] | 0
A | SUPERVISION |  | 10%= | 345.5 | AJUSTMENT= |  | 345.5
| 253 - PIPING MATERIAL CONTROLS TOTAL - LABOR HRS | [6 empty] | 3800.5 | 13.74% | [6 empty] | 0
2011-106 | [10 empty] | 2011-106
254. . . . P I P E S T R E S S E N G I N E E R I N G | [6 empty] | ESTIMATE |  | NOTES: | [5 empty] | FINAL
| SPECIFICATIONS | SPEC NO. |  | QUANTITY | HOURS | DEFAULT | LABOR HRS | TOTAL LABOR HRS | [5 empty] | QUANTITY | HRS | TOTAL LABOR HRS
B | ANALYSIS | 54001 |  | 1 |  | 20 | 20
B | PRE ENG & ENG SUPPTS | 54040 |  | 1 |  | 20 | 20
B | COMPONENTS (EXP JTS, STRUTS, ETC) |  |  | 0 |  | 10 | 0
B | OTHER |  |  | 0 |  | 20 | 0
| TOTAL NUMBER OF SPECIFICATIONS AND MAN HOURS | [5 empty] | 40 | [6 empty] | 0 | 0
| ACTIVITIES |  |  | QUANTITY | HOURS | DEFAULT | LABOR HRS | [7 empty] | HRS
D | STRESS ANALYSIS ACTIVITIES | HRS. PER LINE ACTUAL |  | 500 |  | 10 | 5000
E | STRESS ANALYSIS PRODUCT DRAWIBGS | HRS. PER PRODUCT ACTUAL |  | 10 |  | 8 | 80
SUB-TOTAL ACTIVITY LABOR HOURS
A | SUPERVISION |  | 10%= | 504 | AJUSTMENT= |  | 504
| 254 - PIPE STRESS ENGINEERING TOTAL -LABOR HRS | [6 empty] | 5624 | 20.33% | [6 empty] | 0
[6 empty] | TECH. TOTAL |  | 25536.2 | [7 empty] | 0
2011-106 | [10 empty] | 2011-106
250 . . . . L E A D P I P I N G E N G I N E E R | [6 empty] | ESTIMATE |  | NOTES: | [5 empty] | FINAL
| ACTIVITIES |  |  | NUMBER | HOURS | DEFAULT | LABOR HRS | TOTAL LABOR HRS | [6 empty] | LABOR HRS | TOTAL LABOR HRS
B | LPE FIELD TRIPS - PRELIM. JOB SITE SURVEY |  | DAYS | 26 | 4 | 8 | 104
E | CONSTRUCTION WORK PACKAGE PREP |  | EACH | 17 |  | 20 | 340
X | TRIPS - CONSTRUCTION SUPPORT | PEOPLE WEEKS x 40 HRS | PEOPLE | 0 |  | 40 | 0
X | TRIPS - PIPE FAB SHOP SURVEY ( INSPECT./QUALIFY) |  | DAYS | 0 |  | 8 | 0
A | DEPARTMENT MANAGEMENT REVIEWS | Q.A. AUDIT ACTIVITIES | DAYS | 35 | 2 | 8 | 70
A | TECHNICAL SUPPORT ACTIVITIES |  | DAYS | 130 | 2 | 8 | 260
A | TECHNICAL AIDE | PEOPLE WEEKS x 40 HRS | WEEKS | 26 |  | 40 | 1040
B | FRONT END PLANNING (SCOPE, EST, ETC) | [5 empty] | 120
A | SUPERVISION / COORDINATION / MEETINGS |  | 10%= | 193.4 | AJUSTMENT= |  | 193.4
| 250 - LEAD PIPING ENGINEER & STAFF -TOTAL LABOR HRS |  |  |  |  | FLWB |  | 2127.4 | 7.69% | [6 empty] | 0
"X" = Activity that is required but will be handled under a different budget. |  |  |  |  | PROJECT OR JOB TOTAL |  |  | 27663.6 | 100 | % | [5 empty] | 0 | 100 | %