## Time Charge Codes
Piping Group Time Charge Codes
Activity Grouping | Acitivity Code | Piping Sub-Group Operation Number & Name (*)
|  | 250 | 251 | 252 | 253 | 254
|  | PEL | PME | PDG | PMC | PSE
Supervision | A | Work Assignment, Planning, Status Report Meetings w/ Department, Project & Client, Emp.. Perform. Reviews, Technical Direction, P&ID Reviews | Work Assignment, Work review, Meetings, Status Reports, Emp.. Perform. Review, P&ID Reviews | Work Assignment, Work review, Meetings, Status Reports, Emp.. Perform. Review, P&ID Reviews | Work Assignment, Work review, Meetings, Status Reports, Emp.. Perform. Review, P&ID Reviews | Work Assignment, Work review, Meetings, Status Reports, Emp.. Perform. Review, P&ID Reviews
Project Design Basis | B | SOW, Labor Hour Estimate, Control Level Schedule, Collect, Review and Disseminate Client Criteria, Coordinate Vendor SQ CK, Field Trips | Specifications, Standards, Develop CCC, Vendor Data SQ CK | Specifications, Standards, Plot Plan Developm't, Vendor Data SQ CK, Heat Tracing Criteria, Field Trips | Establish Mat'l Take-Off Data Base, Define Material "Bump" Criteria, | Specifications, Standards, Define Pipe Stress Analysis Criteria, Pre-Eng. Pipe Supports Vendor Data SQ CK
Preliminary Design | C |  |  | Transpositions, Vessel Orientations, Model Index, Drawing Index, Layout Studies, | Preliminary MTO & RFQ
Detailed Design | D | Model Reviews | SP Item Activities, Model Reviews, | 2D CADD, 3D CADD, Manual Drawings, Revise Exist. Dwgs.,Model Reviews, | Intermediate MTO and POR, Model Reviews | Model Reviews, Pipe Stress Analysis, Hanger Data Sheets, Joint Data Sheets, Review & Sign Isometrics
Deliverables | E | Construction Work Packages (CWP) | Line List | Manual Isometrics, CADD Isometrics, Piping Plans, Piping Sections, Isometric Index, Tie-In Index, Tie-In List, Tie-In Isos., Heat Tracing Isometrics, Heat Tracing Index, Demo Dwg's, | Final MTO, PO Supplements, Shortage Reports, Overage Reports,
Services | F |  |  | CADD Coordinator
(*) Definition of Piping Sub-Group Numbers & Names
250 - PEL = Piping Engineering Lead (See Company Job Description)
251 - PME = Piping Material Engineer (See Company Job Description)
252 - PDG = Piping Design Group (See Company Job Description)
253 - PMC = Piping Material Control (See Company Job Description)
254 - PSE = Piping Stress Engineering (See Company Job Description)

## Estimate Summary Form
PIPING ENGINEERING AND DESIGN __ SUMMARY OF HOME OFFICE LABOR AND COST ESTIMATE & FINAL REPORT
PROJECT NAME: |  | PROJECT MANAGER:
CLIENT: |  | PREPARED BY (LPE): |  |  |  |  | EST. LINE COUNT: |  | 0
LOCATION: |  | APPROVED BY: |  |  |  |  | EQUIV. ISO. COUNT:
PROJECT NO.: | 0 | FINAL REPORT BY: |  |  |  |  | EST. TIC: ($MM)
PLANT TYPE: |  |  | REV.: | 0 | 1
CONTRACT TYPE : |  | (EPC, EPCM, etc.) | DATE: |  |  |  | FINAL ISO COUNT : |  | 0
PIPING ENGINEERING |  | DISCIPLINE ESTIMATE |  |  |  | APPV'D BUDGET |  | FINAL REPORT
OPER. No. | GROUP | ESTIMATED LABOR HOURS | % OF TOTAL | ESTIMATED COMPUTER EXPENSES $ | ESTIMATED TRAVEL & LODGING EXPENSES $ | BUDGET LABOR HOURS | % OF TOTAL | ACTUAL LABOR HOURS | % OF TOTAL
251 | PIPE MATERIAL ENGR. | #VALUE! | #VALUE! |  |  |  |  | 0
252 | PIPING DESIGN | #VALUE! | #VALUE! |  |  |  |  | 0
253 | PIPE MATERIAL CONTROL | #VALUE! | #VALUE! |  |  |  |  | 0
254 | PIPE STRESS ENGR. | #VALUE! | #VALUE! |  |  |  |  | 0
SUB TOTAL TECHNICAL LABOR HRS = |  | #VALUE! |  | 0 | 0 | 0 |  | 0
250 | LPE, DEPT. & STAFF | #VALUE! | #VALUE! |  |  |  |  | 0
ALL | TOTAL LABOR HOURS | #VALUE! | 100 % |  |  | 0 | 100 % | 0 | 100 %
REMARKS: |  | HRS/ISO= | #VALUE! |  |  | HRS/ISO= | #VALUE! | HRS/ISO = | #VALUE!

## Estimate Detail Form
PIPING ENGINEERING & DESIGN HOME OFFICE LABOR, EXPENSE ESTIMATE DETAIL | [10 empty] | PIPING ENGINEERING & DESIGN FINAL REPORT DETAIL
|  |  |  | PLEASE NOTE Only the yellow boxes are for data entry | [9 empty] | The area below is to be used only at the end of the project to record the historical actual data.
PROJECT NO.
0
251. . . . P I P I N G M A T E R I A L E N G I N E E R I N G | [6 empty] | ESTIMATE |  | NOTES: | [5 empty] | FINAL
| SPECIFICATIONS | SPEC NO. |  | QUANTITY | HOURS | DEFAULT | LABOR HRS | TOTAL LABOR HRS | [5 empty] | QUANTITY | LABOR HRS | TOTAL LABOR HRS
B | PIPING MAT'L LINE CLASS NOTES & DATA |  |  |  |  | 20 | 0
B | INDIVIDUAL LINE CLASS SPECS |  |  |  |  | 20 | 0
B | PURCHASE (PIPE, VALVES, FITTINGS, ETC.) |  |  |  |  | 5 | 0
B | TESTING, CLEANING, PASSIVATING |  |  |  |  | 20 | 0
B | SP ITEM - SPEC, LIST, & DATASHEETS |  |  |  |  | 8 | 0
B | ISULATING,PAINTING,COATING,LINING |  |  |  |  | 20 | 0
B | WELDING / NDE |  |  |  |  | 20 | 0
| TOTAL NUMBER OF SPECIFICATIONS AND HOURS |  |  |  | 0 | [9 empty] | 0
| ACTIVITIES | [5 empty] | LABOR HRS | [7 empty] | LABOR HRS
B | PROJECT COMMODITY CATLAOG | [11 empty] | ACTUAL.
E | LINE LIST / INDEX - DEVELOP & MAINTAIN |  | EST. LINE COUNT |  |  | 0.5 | [6 empty] | LINE No. =
| SUB-TOTAL ACTIVITY MAN HOURS | [5 empty] | #VALUE!
A | SUPERVISION |  | 10%= | #VALUE! | AJUSTMENT |  | #VALUE!
| 252--PIPING MATERIAL ENGINEERING TOTALS - HRS | [6 empty] | #VALUE! | #VALUE! | [6 empty] | 0
0 | [10 empty] | 0
252 . . . . P I P I N G D E S I G N | [6 empty] | ESTIMATE | [6 empty] | FINAL
| ACTIVITY |  |  | NUMBER | HOURS | [6 empty] | SCALE | NUMBER | AVG. HOURS
| DRAWINGS/DOCUMENTS | SCALE | SIZE | OF | PER | DEFAULT |  | TOTAL LABOR HRS |  |  | SIZE | OF | OF | PER | LABOR | TOTAL LABOR HRS
| ( DWG. SIZE= A - B - C - D - E ) | (OPTIONAL) | (OPTIONAL) | ITEMS | ITEM | HRS | LABOR HRS |  |  |  |  | DRAWINGS | DRAWINGS | DRAWING | HRS
C | TRANSPOSITION LAYOUTS (NON CAD) |  |  |  |  | 100 | 0 | [6 empty] | #DIV/0!
C | LAYOUTS, STUDIES, VESSEL ORIENTATIONS |  |  |  |  | 40 | 0 | [6 empty] | #DIV/0!
C | LOCATION CONTROL PLANS (LCP) |  |  |  |  | 120 | 0 | [6 empty] | #DIV/0!
C | PLOT PLANS (SITE AND/OR UNIT) |  |  |  |  | 100 | 0 | [6 empty] | #DIV/0!
C | PIPING INDEX ( PLANS, MODEL, TIE-IN ) |  |  |  |  | 20 | 0 | [6 empty] | #DIV/0!
B | DRAWING /VENDOR PRINT SQ. CK. | VARIOUS | VARIOUS |  |  | 1 | 0 | [6 empty] | #DIV/0!
D | PIPING PLAN DRAWINGS ( 2D/MANUAL) |  |  |  |  | 141 | 0 | [6 empty] | #DIV/0!
D | 3D MODELING - EQUIPMENT |  |  |  |  | 6 | 0 | [6 empty] | #DIV/0!
D | 3D MODELING - PIPE LINES |  |  |  |  | 4 | 0 | [6 empty] | #DIV/0!
B | PIPING STANDARD & DETAIL DRAWINGS |  |  |  |  | 40 | 0
E | HEAT TRACE DRAWINGS (PIPING ONLY) |  |  |  |  | 4.25 | 0
E | DEMOLITION DRAWINGS ( NON-CAD) |  |  |  |  | 15 | 0
E | ISOMETRICS (NEW LINES & TIE-INS) | N/A |  |  |  | 8.25 | 0
E | PIPING PLAN DRAWINGS (REV EXIST'G) |  |  |  |  | 40 | 0
E | PIPING PLAN - AS-BUILTS * |  |  |  |  | 20 | 0
E | EXTRACT PLAN DRAWINGS - 3D |  |  |  |  | 20 | 0
E | EXTRACT ISOMETRICS - 3D |  |  |  |  | 1 | 0
| SUB-TOTAL DRAWING QUANTITIES AND LABOR HOURS |  |  | 0 |  |  | 0 | [5 empty] | 0 | #DIV/0! | 0
| SPECIFICATIONS | SPEC NO. |  | QUANTITY | HRS. PER. | DEFAULT | HRS |  | NOTES: |  |  |  |  | QUANTITY | HRS
B | DESIGN, LAYOUT & DRAWING |  |  |  |  | 10 | 0
B | SHOP FABRICATION |  |  |  |  | 10 | 0
B | FIELD FABRICATION |  |  |  |  | 10 | 0
B | TIE INS |  |  |  |  | 10 | 0
B | GEOGRAPHIC COLOR CODE |  |  |  |  | 10 | 0
B | HEAT TRACING |  |  |  |  | 10 | 0
| SUB-TOTAL NUMBER OF SPECIFICATIONS AND LABOR HOURS | [5 empty] | 0 | [6 empty] | 0 | 0
| ACTIVITY |  |  | QUANTITY | HRS. PER. | DEFAULT | HRS | [6 empty] | QUANTITY | HRS
B | DESIGNER FIELD TRIPS | DAYS / HOURS |  |  |  | 8 | 0
E | TIE IN LIST | No TIE-INS/ HRS PER |  |  |  | 1 | 0
F | CAD COORDINATOR | WEEKS / HOURS |  |  |  | 40 | 0
E | ISOMETRIC DRAWING LIST/INDEX | ISOMETRIC COUNT | = |  |  | 1 | 0
| SUB-TOTAL ACTIVITY LABOR HOURS | [5 empty] | 0 | [7 empty] | 0
A | SUPERVISION |  | 10%= | #VALUE! | AJUSTMENT= |  | #VALUE!
| 251 - PIPING DESIGN TOTALS - DWGS, SPECS, LABOR HOURS | [6 empty] | #VALUE! | #VALUE! | [6 empty] | 0
0 | [10 empty] | 0
253 . . . . P I P I N G M A T E R I A L C O N T R O L | [6 empty] | ESTIMATE |  | NOTES: | [5 empty] | FINAL
| ACTIVITIES |  |  | QUANTITY | HRS. PER. | DEFAULT | HRS | TOTAL LABOR HRS | [5 empty] | QUANTITY | LABOR HRS | TOTAL LABOR HRS
B | MATERIAL MANAGEMENT CRITERIA, P&ID REVIEW |  |  |  |  | 3 | 0
C | MAT'L TAKEOFF (PRELIM) & RFQ | PER EQIV. ISO |  |  |  | 0.5 | 0
D | MAT'L TAKEOFF (INTERMEDIATE) & PO | PER EQIV. ISO |  |  |  | 1 | 0
E | MAT'L TAKEOFF (FINAL,MANUAL) & SUPPL. | PER ISO |  |  |  | 1 | 0
E | MAT'L TAKEOFF (FINAL, DOWNLOAD) & SUPPL. | PER ISO |  |  |  | 0.5 | 0
E | MATERIAL OVERAGE?SHORTAGE REPORTS. | PER RFQ/PO, ETC |  |  |  | 80 | 0
| SUB-TOTAL ACTIVITY MAN HOURS | [5 empty] | 0 | [7 empty] | 0
A | SUPERVISION |  | 10%= | #VALUE! | AJUSTMENT= |  | #VALUE!
| 253 - PIPING MATERIAL CONTROLS TOTAL - LABOR HRS | [6 empty] | #VALUE! | #VALUE! | [6 empty] | 0
0 | [10 empty] | 0
254. . . . P I P E S T R E S S E N G I N E E R I N G | [6 empty] | ESTIMATE |  | NOTES: | [5 empty] | FINAL
| SPECIFICATIONS | SPEC NO. |  | QUANTITY | HOURS | DEFAULT | LABOR HRS | TOTAL LABOR HRS | [5 empty] | QUANTITY | HRS | TOTAL LABOR HRS
B | ANALYSIS |  |  |  |  | 20 | 0
B | PRE ENG & ENG SUPPTS |  |  |  |  | 20 | 0
B | COMPONENTS (EXP JTS, STRUTS, ETC) |  |  |  |  | 10 | 0
B | OTHER |  |  |  |  | 20 | 0
| TOTAL NUMBER OF SPECIFICATIONS AND MAN HOURS | [5 empty] | 0 | [6 empty] | 0 | 0
| ACTIVITIES |  |  | QUANTITY | HOURS | DEFAULT | LABOR HRS | [7 empty] | HRS
D | STRESS ANALYSIS ACTIVITIES | HRS. PER LINE ACTUAL |  |  |  | 10 | 0
SUB-TOTAL ACTIVITY LABOR HOURS
A | SUPERVISION |  | 10%= | #VALUE! | AJUSTMENT= |  | #VALUE!
| 254 - PIPE STRESS ENGINEERING TOTAL -LABOR HRS | [6 empty] | #VALUE! | #VALUE! | [6 empty] | 0
[7 empty] | TECH. TOTAL | #VALUE! | [7 empty] | 0
0 | [10 empty] | 0
250 . . . . L E A D P I P I N G E N G I N E E R | [6 empty] | ESTIMATE |  | NOTES: | [5 empty] | FINAL
| ACTIVITIES |  |  | NUMBER | HOURS | DEFAULT | LABOR HRS | TOTAL LABOR HRS | [6 empty] | LABOR HRS | TOTAL LABOR HRS
B | LPE FIELD TRIPS - PRELIM. JOB SITE SURVEY |  | DAYS |  |  | 8 | 0
E | CONSTRUCTION WORK PACKAGE PREP |  | EACH |  |  | 20 | 0
X | TRIPS - CONSTRUCTION SUPPORT | PEOPLE WEEKS x 40 HRS | PEOPLE |  |  | 40 | 0
X | TRIPS - PIPE FAB SHOP SURVEY ( INSPECT./QUALIFY) |  | DAYS |  |  | 8 | 0
A | DEPARTMENT MANAGEMENT REVIEWS | Q.A. AUDIT ACTIVITIES | DAYS |  |  | 8 | 0
A | TECHNICAL SUPPORT ACTIVITIES |  | DAYS |  |  | 8 | 0
A | TECHNICAL AIDE | PEOPLE WEEKS x 40 HRS | WEEKS |  |  | 40 | 0
B | FRONT END PLANNING (SCOPE, EST, ETC)
A | SUPERVISION / COORDINATION / MEETINGS |  | 10%= | #VALUE! | AJUSTMENT= |  | #VALUE!
| 250 - LEAD PIPING ENGINEER & STAFF -TOTAL LABOR HRS |  |  |  |  | FLWB |  | #VALUE! | #VALUE! | [6 empty] | 0
"X" = Activity that is required but will be handled under a different budget. |  |  |  |  | PROJECT OR JOB TOTAL |  |  | #VALUE! | 100 | % | [5 empty] | 0 | 100 | %