## PRELIM EST STAFF PLAN
INITIAL ESTIMATED LABOR HOURS & PRELIMINARY STAFFING PLAN BASED ON HISTORICAL HOURS PER LINE NUMBER
Use this sheet early in project to estimate hours and staffing using P&IDs. Count the number of lines on the P&IDs. Factor the all-in Labor hours at 30 hrs. to 40 hrs per line depending on plant complexity and past performance.
WEEK
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Body count =
Base case work week hours = | 40 | Hours per week - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total spread of hours - |  | 0
Estimated count of line numbers -
Hours per line number -
Estimated total hours - |  | 0
Input in yellow areas only.
Blue areas contain formulas.
If your company standard work week is different than the "40" shown here then enter the proper number in cell "F7".

## CONTROL LEVEL SCHED
PIPING CONTROL LEVEL SCHEDULE
|  |  | NOTE: CELLS WITH BLUE TEXT CONTAIN FORMULARS | [8 empty] | LEGEND: |  |  |  |  | (1) Enter the appropreate Monday Dates (Week Beginning) in "R 15" Cell. All the other cells on Row 15 will fill automatically. (2) Enter the appropreate Friday Dates (Week Ending) in "R 16" Cell. All other Cells on Row 16 will fill automatically. (3) Enter appropreate Month and Year in cell "R 14" where approprate.
| TITLE BLOCK |  | INPUT IN YELLOW AREAS ONLY | [8 empty] | P=PLANNED MANHOUR SPREAD
| PIPING LEAD: |  |  | PHONE: | [7 empty] | A=ACTUAL MANHOUR SPREAD
| PROJECT NAME: | [5 empty] | If your company standard work week is different than the value shown in cell K10 then enter the proper number equal to the correct work week hours. |  |  |  |  | F=FORECAST MANHOUR SPREAD
| PROJ DESCRIPTION: | [10 empty] | DCN= DESIGN CHANGE NOTICE
| CLIENT: | [10 empty] | MO/YR= MONTH/YEAR |  |  |  | MILE-STONES
| LOCATION: | [10 empty] | W/B= WEEK BEGINNING
| DATE: | 2026-07-29 07:25 | [9 empty] | W/E= WEEK ENDING
| SHEET: | 1 OF 1 |  |  |  |  | Standard work week hours = |  |  | 40 |  | ACT= ACTUAL
| LAST UPDATE: | [10 empty] | FOR=FORCAST
LINE | PIPING | PIPING GROUP | HOURS |  |  | EXP'D |  | L A B O R H O U R S | [7 empty] | WEEK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104
| GROUP | ACTIVITY OR TASK | QTY | QTY | PHY % | % | PLAN'D | ORIG | PEND- | UN- | CURR'T |  | FORCAST | DESIGNER/ | PLAN | MO/YR
| IDENTIFICATION | DESCRIPTION | ORIG | CURR | COMP | COMP | CADD | BUDGET | ING | APP'D | BUDGET | ACTUAL | TO | WORK BUDGET/ | ACTUAL | W/B | 2011-07-04 | 2011-07-11 | 2011-07-18 | 2011-07-25 | 2011-08-01 | 2011-08-08 | 2011-08-15 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-09-12 | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2011-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02 | 2012-04-09 | 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06 | 2012-08-13 | 2012-08-20 | 2012-08-27 | 2012-09-03 | 2012-09-10 | 2012-09-17 | 2012-09-24 | 2012-10-01 | 2012-10-08 | 2012-10-15 | 2012-10-22 | 2012-10-29 | 2012-11-05 | 2012-11-12 | 2012-11-19 | 2012-11-26 | 2012-12-03 | 2012-12-10 | 2012-12-17 | 2012-12-24 | 2012-12-31 | 2013-01-07 | 2013-01-14 | 2013-01-21 | 2013-01-28 | 2013-02-04 | 2013-02-11 | 2013-02-18 | 2013-02-25 | 2013-03-04 | 2013-03-11 | 2013-03-18 | 2013-03-25 | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06 | 2013-05-13 | 2013-05-20 | 2013-05-27 | 2013-06-03 | 2013-06-10 | 2013-06-17 | 2013-06-24
[7 empty] | HRS |  | DCN'S | DCN'S |  |  | COMP | (ACT+FOR) | FORCAST | W/E | 2011-07-08 | 2011-07-15 | 2011-07-22 | 2011-07-29 | 2011-08-05 | 2011-08-12 | 2011-08-19 | 2011-08-26 | 2011-09-02 | 2011-09-09 | 2011-09-16 | 2011-09-23 | 2011-09-30 | 2011-10-07 | 2011-10-14 | 2011-10-21 | 2011-10-28 | 2011-11-04 | 2011-11-11 | 2011-11-18 | 2011-11-25 | 2011-12-02 | 2011-12-09 | 2011-12-16 | 2011-12-23 | 2011-12-30 | 2012-01-06 | 2012-01-13 | 2012-01-20 | 2012-01-27 | 2012-02-03 | 2012-02-10 | 2012-02-17 | 2012-02-24 | 2012-03-02 | 2012-03-09 | 2012-03-16 | 2012-03-23 | 2012-03-30 | 2012-04-06 | 2012-04-13 | 2012-04-20 | 2012-04-27 | 2012-05-04 | 2012-05-11 | 2012-05-18 | 2012-05-25 | 2012-06-01 | 2012-06-08 | 2012-06-15 | 2012-06-22 | 2012-06-29 | 2012-07-06 | 2012-07-13 | 2012-07-20 | 2012-07-27 | 2012-08-03 | 2012-08-10 | 2012-08-17 | 2012-08-24 | 2012-08-31 | 2012-09-07 | 2012-09-14 | 2012-09-21 | 2012-09-28 | 2012-10-05 | 2012-10-12 | 2012-10-19 | 2012-10-26 | 2012-11-02 | 2012-11-09 | 2012-11-16 | 2012-11-23 | 2012-11-30 | 2012-12-07 | 2012-12-14 | 2012-12-21 | 2012-12-28 | 2013-01-04 | 2013-01-11 | 2013-01-18 | 2013-01-25 | 2013-02-01 | 2013-02-08 | 2013-02-15 | 2013-02-22 | 2013-03-01 | 2013-03-08 | 2013-03-15 | 2013-03-22 | 2013-03-29 | 2013-04-05 | 2013-04-12 | 2013-04-19 | 2013-04-26 | 2013-05-03 | 2013-05-10 | 2013-05-17 | 2013-05-24 | 2013-05-31 | 2013-06-07 | 2013-06-14 | 2013-06-21 | 2013-06-28
| 251 | A |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
1 | PIPING MATERIAL | SUPERVISION | [9 empty] | 0 |  |  | A
| ENGINEER | [11 empty] | 0 | 0 | F
| 251 | B |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
2 | PIPING MATERIAL | PROJECT DESIGN | [9 empty] | 0 |  |  | A
| ENGINEER | BASIS | [10 empty] | 0 | 0 | F
| 251 | C |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
3 | PIPING MATERIAL | PRELIMINARY DESIGN | [9 empty] | 0 |  |  | A
| ENGINEER | [11 empty] | 0 | 0 | F
| 251 | D |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
4 | PIPING MATERIAL | DETAILED DESIGN | [9 empty] | 0 |  |  | A
| ENGINEER | [11 empty] | 0 | 0 | F
| 251 | E |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
5 | PIPING MATERIAL | DELIVERABLES | [9 empty] | 0 |  |  | A
| ENGINEER | [11 empty] | 0 | 0 | F | 0
| 252 | A |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
6 | PIPING DESIGN | SUPERVISION | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 252 | B |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
7 | PIPING DESIGN | PROJECT DESIGN | [9 empty] | 0 |  |  | A
|  | BASIS | [10 empty] | 0 | 0 | F
| 252 | C |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
8 | PIPING DESIGN | PRELIMINARY DESIGN | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 252 | D |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
9 | PIPING DESIGN | DETAILED DESIGN | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 252 | E |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
10 | PIPING DESIGN | DELIVERABLES | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 252 | F |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
11 | SERVICES | CADD COORDINATION | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F | 0
| 253 | A |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
12 | MAT'L CONTROL | SUPERVISION | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 253 | B |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
13 | MAT'L CONTROL | PROJECT DESIGN | [9 empty] | 0 |  |  | A
|  | BASIS | [10 empty] | 0 | 0 | F
| 253 | C |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
14 | MAT'L CONTROL | PRELIMINARY DESIGN | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 253 | D |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
15 | MAT'L CONTROL | DETAILED DESIGN | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 253 | E |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
16 | MAT'L CONTROL | DELIVERABLES | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F | 0
| 254 | A |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
17 | PIPE STRESS | SUPERVISION | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 254 | B |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
18 | PIPE STRESS | PROJECT DESIGN | [9 empty] | 0 |  |  | A
|  | BASIS | [10 empty] | 0 | 0 | F
| 254 | C |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
19 | PIPE STRESS | PRELIMINARY DESIGN | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 254 | D |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
20 | PIPE STRESS | DETAILED DESIGN | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 254 | E |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
21 | PIPE STRESS | DELIVERABLES | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F | 0
| 250 | A |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
22 | PIPING LEAD | SUPERVISION | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 250 | B |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
23 | PIPING LEAD | PROJECT DESIGN | [9 empty] | 0 |  |  | A
|  | BASIS | [10 empty] | 0 | 0 | F
| 250 | C |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
24 | PIPING LEAD | PRELIMINARY DESIGN | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 250 | D |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
25 | PIPING LEAD | DETAILED DESIGN | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F
| 250 | E |  | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  |  | P | 0
26 | PIPING LEAD | DELIVERABLES | [9 empty] | 0 |  |  | A
[13 empty] | 0 | 0 | F | 0
[7 empty] | T O T A L S | [7 empty] | WEEK |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104
[7 empty] | ORIGINAL BUDGET |  |  | 0 |  |  |  |  | WEEK | W/B | 2011-07-04 | 2011-07-11 | 2011-07-18 | 2011-07-25 | 2011-08-01 | 2011-08-08 | 2011-08-15 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-09-12 | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2011-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02 | 2012-04-09 | 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06 | 2012-08-13 | 2012-08-20 | 2012-08-27 | 2012-09-03 | 2012-09-10 | 2012-09-17 | 2012-09-24 | 2012-10-01 | 2012-10-08 | 2012-10-15 | 2012-10-22 | 2012-10-29 | 2012-11-05 | 2012-11-12 | 2012-11-19 | 2012-11-26 | 2012-12-03 | 2012-12-10 | 2012-12-17 | 2012-12-24 | 2012-12-31 | 2013-01-07 | 2013-01-14 | 2013-01-21 | 2013-01-28 | 2013-02-04 | 2013-02-11 | 2013-02-18 | 2013-02-25 | 2013-03-04 | 2013-03-11 | 2013-03-18 | 2013-03-25 | 2013-04-01 | 2013-04-08 | 2013-04-15 | 2013-04-22 | 2013-04-29 | 2013-05-06 | 2013-05-13 | 2013-05-20 | 2013-05-27 | 2013-06-03 | 2013-06-10 | 2013-06-17 | 2013-06-24
[7 empty] | PENDING DCN's |  |  | 0 |  |  | PLANNED INCREMENT |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | UN-APP'D DCN's |  |  | 0 |  |  | PLANNED CUMULATIVE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
[7 empty] | CURRENT BUDGET |  |  | 0 |  |  | STAFFING (40 hr/week) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | EXPENDED HOURS |  |  | 0 |  |  | ACTUAL INCREMENT |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | FORECAST HOURS |  |  | 0 |  |  | ACTUAL CUMULATIVE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
[7 empty] | PROJ'D TOTAL (exp'd + fore) |  |  | 0 |  |  | STAFFING (40 hr/week) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | PERCENT COMPLETE |  |  | #DIV/0! |  |  | FORECAST INCREMENT |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | PERCENT EXPENDED |  |  | #DIV/0! |  |  | FORECAST CUMULATIVE |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
[7 empty] | PRODUCTIVITY FACTOR |  |  | #DIV/0! |  |  | STAFFING (40 hr/week) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | PLAN CAD HRS |  |  | 0
[7 empty] | FORECAST CAD HRS |  |  | 0 |  |  | PLANNED CAD HOURS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | FORECAST CAD HOURS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: CADD Hours are only of interest if your Company or Project charges for CADD hours as a separate cost line item.