## INSTRUCTIONS
Physical Percent Complete Status Report
Warning
This Excel Worksheet or Workbook "Tool" is locked and password protected. The user may only enter date in the "yellow" cells. Other cells on this "Tool" includes locked "cells" that contain complex math formulas. Care should be taken to learn where these cells are and if the spreadsheet is ever unlocked that the cells with the formulas are not disturbed. Disturbing or altering these cells may render the "Tool" unable to function properly.
Introduction
This WorkBook "Tool" is part of a suite of 6 "Tools" that are intended to aid the Piping Engineering Lead (Senior Supervisor or whatever he or she is called) who has the responsibility to make estimates, schedules, control the work, the hours, report the progress and prepare & files the Final Job Report. These "Tools" are: (1) Piping Engineering & Design Scope of Work, (3) Piping Labor Hour Estimating Forms, (3) Piping Control Level Schedule, (4) Physical Percent Complete Status Report, (5) Design Change Notice and (6) "Janus" Historical Data Log. These 5 WorkBook Tools are intended to be used as a "Set" and will bring value to your effort only if you in fact use all of them.
Instruction # 1
Study the instructions for this WorkBook. If you have any questions about anything here please contact me via E-mail (jopennock@netscape.net) and I will help you.
Instruction # 2
The Prerequisite for the use of this tool is a completed and approved Scope of Work (SOW), Labor Hour Estimate and Control Level Schedule.
Instruction # 3
Fill out the yellow boxes in the title Block area.
Instruction # 4
"Individual Activity Status enter a value (0% to 100%) for the activities that have been worked on or are completed. A 0% value may be entered if desirable for activities that that have not started.
Instruction # 5
Use the "Remarks" column if it is important to explain why some activity is ahead or behind schedule.
Instruction # 6
In the cell "GH 4" enter the total approved labor hours. In the cell "IJ 4" enter the current Hours used as of the report date. All other data is automatic.
Instruction #7
If you need to add, delete or modify any of the Activities in the "C" column you must use the pass word and unlock the sheet. When you make such a change you must also make appropriate changes to the "D" column so that the total at the bottom of Column "D" still adds up to 100%. When your changes are complete you are advised to re-lock the sheet.

## SAMPLE STATUS FORM
Piping Physical Percent Completion Status |  |  |  |  | Rev./Rpt. Date: | 2011-11-09 | Physical % Complete: | 57.2% | Productive Factor: | 1.0225
Proj. Name | Temple Refinery Upgrade | Project No. | 2011-106 |  | Approved Budget Hours |  | Hrs used to date |  | % Hours Used
Proj. Mngr. | Al Demming | Piping Lead | A. R. Tennyson |  | 27668 |  | 15478 |  | 55.94%
Item No. | Activity | Activity Base Value | Activity Status (% Complete) | Activity % Complete Value | Comments
1 | Client Approved Scope of Work | 1% | 100% | 1%
2 | Home Office Labor Hour Estimate | 1% | 100% | 1%
3 | Piping Control Level Schedule | 1% | 100% | 1%
3 | Process Graphics Support (P&ID, PFD, Util., etc) | 1% | 100% | 1%
4 | Client Approved Specifications | 3% | 100% | 3%
5 | Client Approved Standards | 2% | 100% | 2%
6 | Client Approved Plot Plan | 3% | 100% | 3%
7 | Piping Layouts & Studies | 2% | 95% | 1.9%
8 | Piping Underground Layout (Manual or CAD) | 2% | 100% | 2%
9 | Vessel Orientation Layouts | 5% | 90% | 4.5%
10 | Preliminary Material Take-Off (1st MTO) | 2% | 100% | 2%
11 | 3D Data Base Loaded | 5% | 100% | 5%
12 | 3D Model Partitions Defined | 2% | 100% | 2%
13 | Modeling of Vessels % Tanks (create and check) | 3% | 100% | 3%
14 | Receive Vendor Outlines (pump, exch, heater) | 4% | 80% | 3.2% | 10 Pumps, 6 Exchangers & I Heater still short Vendor "Certified"
15 | Model Vendor Equipment (create & check) | 3% | 50% | 1.5%
16 | Piping/Structural Sketches & Coordination | 2% | 100% | 2%
17 | Piping/Electrical Coordination | 2% | 100% | 2%
18 | Piping/Instrument Coordination | 2% | 100% | 2%
19 | Modeling of Piping (Alloy and Large Sizes) | 9% | 60% | 5.4%
20 | Modeling of Piping (Intermediate Sizes) | 9% | 45% | 4.05%
21 | Modeling of Piping (All other) | 9% | 35% | 3.15%
22 | Pipe Supports | 1% | 30% | 0.3%
23 | Pipe Stress Analysis | 2% | 30% | 0.6%
24 | Perform Secondary (Intermediate Mat'l Take-Off) | 1% | 0% | 0%
25 | Resolution of Final Interference/Clash Detection | 2% | 0% | 0%
26 | Client Model Review & Approval | 2% | 20% | 0.4%
27 | Extract & Check Isometrics (Alloy & Large Size) | 2% | 10% | 0.2%
28 | Extract & Check Isometrics (Intermediate Size) | 2% | 0% | 0%
29 | Extract & Check Isometrics (All other) | 2% | 0% | 0%
30 | Update Model | 3% | 0% | 0%
31 | Extract & Issue All Shop Fab Isometrics by Priority | 2% | 0% | 0%
32 | Extract & Issue All Field Fab Isometrics by Priority | 2% | 0% | 0%
33 | Perform Final Material Take-Off | 1% | 0% | 0%
34 | Extract Record Piping Drawings & Isometrics | 3% | 0% | 0%
35 | Freeze Model & Transmit Copy to Field | 1% | 0% | 0%
36 | Perform Job Close-Out Duties | 1% | 0% | 0%
37 |  |  |  | 0%
38 |  |  |  | 0%
| Total: | 100% |  | 57.2%

## BLANK STATUS FORM
jop
Piping Physical Percent Completion Status |  |  |  |  | Rev./Rpt. Date: | Physical & Complete: | 0% | Productivity Factor: | #DIV/0!
Proj. Name |  | Project No. |  |  | Approved Budget Hours | Hrs used to date |  | % Hours Used
Proj. Mngr. |  | Piping Lead | [5 empty] | #DIV/0!
Item No. | Activity | Activity Base Value | Activity Status (% Complete) | Activity % Complete Value | Comments
1 | Client Approved Scope of Work | 1% |  | 0%
2 | Home Office Labor Hour Estimate | 1% |  | 0%
3 | Piping Control Level Schedule | 1% |  | 0%
3 | Process Graphics Support (P&ID, Pfd, Util., etc) | 1% |  | 0%
4 | Client Approved Specifications | 3% |  | 0%
5 | Client Approved Standards | 2% |  | 0%
6 | Client Approved Plot Plan | 3% |  | 0%
7 | Piping Layouts & Studies | 2% |  | 0%
8 | Piping Underground Layout (Manual or CAD) | 2% |  | 0%
9 | Vessel Orientation Layouts | 5% |  | 0%
10 | Preliminary Material Take-Off (1st MTO) | 2% |  | 0%
11 | 3D Data Base Loaded | 5% |  | 0%
12 | 3D Model Partitions Defined | 2% |  | 0%
13 | Modeling of Vessels % Tanks (create and check) | 3% |  | 0%
14 | Receive Vendor Outlines (pump, exch, heater) | 4% |  | 0%
15 | Model Vendor Equipment (create & check) | 3% |  | 0%
16 | Piping/Structural Sketches & Coordination | 2% |  | 0%
17 | Piping/Electrical Coordination | 2% |  | 0%
18 | Piping/Instrument Coordination | 2% |  | 0%
19 | Modeling of Piping (Alloy and Large Sizes) | 9% |  | 0%
20 | Modeling of Piping (Intermediate Sizes) | 9% |  | 0%
21 | Modeling of Piping (All other) | 9% |  | 0%
22 | Pipe Supports | 1% |  | 0%
23 | Pipe Stress Analysis | 2% |  | 0%
24 | Perform Secondary (Intermediate Mat'l Take-Off) | 1% |  | 0%
25 | Resolution of Final Interference/Clash Detection | 2% |  | 0%
26 | Client Model Review & Approval | 2% |  | 0%
27 | Extract & Check Isometrics (Alloy & Large Size) | 2% |  | 0%
28 | Extract & Check Isometrics (Intermediate Size) | 2% |  | 0%
29 | Extract & Check Isometrics (All other) | 2% |  | 0%
30 | Update Model | 3% |  | 0%
31 | Extract & Issue All Shop Fab Isometrics by Priority | 2% |  | 0%
32 | Extract & Issue All Field Fab Isometrics by Priority | 2% |  | 0%
33 | Perform Final Material Take-Off | 1% |  | 0%
34 | Extract Record Piping Drawings & Isometrics | 3% |  | 0%
35 | Freeze Model & Transmit Copy to Field | 1% |  | 0%
36 | Perform Job Close-Out Duties | 1% |  | 0%
37 |  |  |  | 0%
38 |  |  |  | 0%
| Total: | 100% |  | 0%