## INSTRUCTIONS
Design Change Notice (DCN)
Warning
This Excel Worksheet or Workbook "Tool" is locked and password protected. The user may only enter date in the "yellow" cells. Other cells on this "Tool" includes locked "cells" that contain complex math formulas. Care should be taken to learn where these cells are and if the spreadsheet is ever unlocked that the cells with the formulas are not disturbed. Disturbing or altering these cells may render the "Tool" unable to function properly.
Introduction
This WorkBook "Tool" is part of a suite of 6 "Tools" that are intended to aid the Piping Engineering Lead (Senior Supervisor or whatever he or she is called) who has the responsibility to make estimates, schedules, control the work, the hours, report the progress and prepare & files the Final Job Report. These "Tools" are: (1) Piping Engineering & Design Scope of Work, (3) Piping Labor Hour Estimating Forms, (3) Piping Control Level Schedule, (4) Physical Percent Complete Status Report, (5) Design Change Notice and (6) "Janus" Historical Data Log. These 5 WorkBook Tools are intended to be used as a "Set" and will bring value to your effort only if you in fact use all of them.
Instruction # 1
Study these instructions and all four of the Worksheets of this WorkBook. If you have any questions about anything here please contact me via E-mail (jopennock@netscape.net) and I will help you.
Instruction # 2
The Prerequisite for the use of this tool is a completed and approved Scope of Work (SOW). Without an approved SOW it is not possible to determine what is included in the original project and what is not a part of the original project.
Instruction # 3
There are two types of "DCN's. There is the Client originated "Change Order" and there is a "Trend" (Scope, Estimate or Schedule Creep) that originates within the Piping effort on the project.
Instruction # 4
To fully understand the difference and the impact of a "Change Orders" and a "Trend" you are advised to read "CONTROLLING CHANGE" (Chapter 15 of the book “Piping Engineering Leadership for Process Plant Projects” by James O. Pennock)

## SAMPLE DCN FORM
Sample "Design Change Notice" #1
Company Name |  |  |  | Design Change Notice |  |  |  | DCN No.
|  |  |  | PIPING ENGINEERING & DESIGN |  |  |  | 50-001
Project Name & No: |  |  | Temple Refinery Upgrades - 2011 - 106
By: |  |  | A. R. Tennyson |  | DCN Type: |  | Change Order | X
Date: |  |  | 2011-09-01 |  |  |  | Trend
General Description: |  |  | Addition of Feed and Product Storage Tanks
Part A - Definition
SCOPE |  |  | Client addition - Tankage capacity increased to meet process conditions and marketing goals.
CAUSE |  |  | Economic evaluation
Part B - IMPACT
Op. | Act. | Group/Activity | Description of added work |  |  |  | Hrs per (1) | Totals
251 | A | PME Supervision
251 | B | PME Proj. Desig Basis
251 | C | PME Preliminary Design
251 | D | PME Detailed Design
251 | E | PME Deliverables | Revise Line List to Add 15 new lines |  |  |  | 15 | 15
252 | A | PDG Supervision |  |  |  |  | 16
252 | B | PDG Proj. Desig Basis | Revises two plot plans & two LCP drawings |  |  |  | 16
252 | C | PDG Preliminary Design
252 | D | PDG Detailed Design | Adds new piping Plan & Section drawings |  |  |  | 100
252 | E | PDG Deliverables | Adds 45 new Isometrics |  |  |  | 360
252 | F | PDG CADD Coord. | [5 empty] | 492
253 | A | PMC Supervision
253 | B | PMC Proj. Desig Basis
253 | C | PMC Preliminary Design | Requires suplimental MTO for new lines and revision to RFP |  |  |  | 45
253 | D | PMC Detailed Design
253 | E | PMC Deliverables | [5 empty] | 45
254 | A | PSE Supervision |  |  |  |  | 8
254 | B | PSE Proj. Desig Basis
254 | C | PSE Preliminary Design
254 | D | PSE Detailed Design | Adds Stress analysis on new pump lines. |  |  |  | 28
254 | E | PSEDeliverables | [5 empty] | 36
250 | A | PEL Supervision | Meetings, Coordination and reporting |  |  |  | 16
250 | B | PEL Proj. Desig Basis | Revise Scope, Estimate and Schedule |  |  |  | 12
250 | C | PEL Preliminary Design
250 | D | PEL Detailed Design
250 | E | PEL Deliverables | [5 empty] | 28
0
0
When "X" is inserted in this box see note (2) - |  |  |  |  | X | Total Labor Hours: |  | 616
DCN DETERMINATION
DCN Action: |  |  | DCN Approved, Proceed: |  | X | Comment
|  |  | DCN Revise and Resubmit: |  |  | Comment
|  |  | DCN Rejected: |  |  | Comment
|  |  | DCN Cancelled: |  |  | Comment
Entity |  |  |  |  | SIGNATURE |  |  | DATE
Piping Department |  |  |  |  | A. G. Patterson |  |  | 2011-09-06
Project Management |  |  |  |  | Al Demming |  |  | 2011-09-09
Client Management |  |  |  |  | G. R. Southerland |  |  | 2011-09-10
(1) - "Hours per" includes: Document development, extraction, editing, corrections, review, approvals and printing.
(2) - When noted ("X") all hours for this DCN will be added to Estmate. and CLS even if "Rejected."
Sample "Design Change Notice" #2
Company Name |  |  |  | Design Change Notice |  |  |  | DCN No.
|  |  |  | PIPING ENGINEERING & DESIGN |  |  |  | 50-002
Project Name & No: |  |  | Temple Refinery Upgrades - 2011 - 106
By: |  |  | A. R. Tennyson |  | DCN Type: |  | Change Order | X
Date: |  |  | 2011-09-01 |  |  |  | Trend
General Description: |  |  | Feed Coalessor added in Unit 14
Part A - Definition
SCOPE |  |  | Feed Coalessor (with Boot) and Pumps added to meet process conditions. Requires elevated Foundation, platforming, Pipe supports, Piping.
CAUSE |  |  | Client Addition - Late feed analysis correction exposed the presents of off-spec contaminates in the raw feed.
Part B - IMPACT
Op. | Act. | Group/Activity | Description of added work |  |  |  | Hrs per (1) | Totals
251 | A | PME Supervision
251 | B | PME Proj. Desig Basis
251 | C | PME Preliminary Design
251 | D | PME Detailed Design
251 | E | PME Deliverables | Revise Line List to add new lines |  |  |  | 10 | 10
252 | A | PDG Supervision
252 | B | PDG Proj. Desig Basis | Revises two plot plans & two LCP drawings |  |  |  | 16
252 | C | PDG Preliminary Design
252 | D | PDG Detailed Design | Model new Equipment and piping |  |  |  | 330
252 | E | PDG Deliverables | Extract and check new Isimetrics |  |  |  | 30
252 | F | PDG CADD Coord. | [5 empty] | 376
253 | A | PMC Supervision
253 | B | PMC Proj. Desig Basis
253 | C | PMC Preliminary Design
253 | D | PMC Detailed Design | Requires MOT and Revision to issued PO |  |  |  | 30
253 | E | PMC Deliverables | [5 empty] | 30
254 | A | PSE Supervision
254 | B | PSE Proj. Desig Basis
254 | C | PSE Preliminary Design
254 | D | PSE Detailed Design | Stress Analysis on some lines |  |  |  | 12
254 | E | PSEDeliverables | [5 empty] | 12
250 | A | PEL Supervision | Meetings, Coordination and reporting |  |  |  | 10
250 | B | PEL Proj. Desig Basis | Revise Scope, Estimate and Schedule |  |  |  | 12
250 | C | PEL Preliminary Design
250 | D | PEL Detailed Design
250 | E | PEL Deliverables | [5 empty] | 22
0
0
When "X" is inserted in this box see note (2) - |  |  |  |  | X | Total Labor Hours: |  | 450
DCN DETERMINATION
DCN Action: |  |  | DCN Approved, Proceed: |  | X | Comment | Must do addition
|  |  | DCN Revise and Resubmit: |  |  | Comment
|  |  | DCN Rejected: |  |  | Comment
|  |  | DCN Cancelled: |  |  | Comment
Entity |  |  |  |  | SIGNATURE |  |  | DATE
Piping Department |  |  |  |  | A. G. Patterson |  |  | 2011-10-04
Project Management |  |  |  |  | Al Demming |  |  | 2011-10-05
Client Management |  |  |  |  | G. R. Southerland |  |  | 2011-10-05
(1) - "Hours per" includes: Document development, extraction, editing, corrections, review, approvals and printing.
(2) - When noted ("X") all hours for this DCN will be added to Estmate. and CLS even if "Rejected."
Sample "Design Change Notice" #3
Company Name |  |  |  | Design Change Notice |  |  |  | DCN No.
|  |  |  | PIPING ENGINEERING & DESIGN |  |  |  | 50-003
Project Name & No: |  |  | Temple Refinery Upgrades - 2011 - 106
By: |  |  | A. R. Tennyson |  | DCN Type: |  | Change Order
Date: |  |  | 2011-09-01 |  |  |  | Trend | X
General Description: |  |  | Recycle work already completed
Part A - Definition
SCOPE |  |  | Equipment size and nozzle locations changed after work was done.
CAUSE |  |  | Vendor error - revised equipment after certified drawing issued
Part B - IMPACT
Op. | Act. | Group/Activity | Description of added work |  |  |  | Hrs per (1) | Totals
251 | A | PME Supervision
251 | B | PME Proj. Desig Basis
251 | C | PME Preliminary Design
251 | D | PME Detailed Design
251 | E | PME Deliverables | [5 empty] | 0
252 | A | PDG Supervision
252 | B | PDG Proj. Desig Basis
252 | C | PDG Preliminary Design
252 | D | PDG Detailed Design | Revise completed work |  |  |  | 50
252 | E | PDG Deliverables | Adds new lines. |  |  |  | 80
252 | F | PDG CADD Coord. | [5 empty] | 130
253 | A | PMC Supervision
253 | B | PMC Proj. Desig Basis
253 | C | PMC Preliminary Design
253 | D | PMC Detailed Design | Revise MTO |  |  |  | 5
253 | E | PMC Deliverables | [5 empty] | 5
254 | A | PSE Supervision
254 | B | PSE Proj. Desig Basis
254 | C | PSE Preliminary Design | Recheck completed work |  |  |  | 10
254 | D | PSE Detailed Design
254 | E | PSEDeliverables | [5 empty] | 10
250 | A | PEL Supervision |  |  |  |  | 7
250 | B | PEL Proj. Desig Basis | No change in scope, but change req'd for Estimate and schedule |  |  |  | 8
250 | C | PEL Preliminary Design
250 | D | PEL Detailed Design
250 | E | PEL Deliverables | [5 empty] | 15
0
0
When "X" is inserted in this box see note (2) - |  |  |  |  | X | Total Labor Hours: |  | 160
DCN DETERMINATION
DCN Action: |  |  | DCN Approved, Proceed: |  |  | Comment
|  |  | DCN Revise and Resubmit: |  |  | Comment
|  |  | DCN Rejected: |  | X | Comment | Judged Normal development?
|  |  | DCN Cancelled: |  |  | Comment
Entity |  |  |  |  | SIGNATURE |  |  | DATE
Piping Department |  |  |  |  | A. G. Patterson |  |  | 2011-09-12
Project Management |  |  |  |  | Al Demming |  |  | 2011-09-12
Client Management |  |  |  |  | G. R. Southerland |  |  | 2011-09-14
(1) - "Hours per" includes: Document development, extraction, editing, corrections, review, approvals and printing.
(2) - When noted ("X") all hours for this DCN will be added to Estmate. and CLS even if "Rejected."

## BLANK DCN FORM
Company Name |  |  | Design Change Notice |  |  |  | DCN No.
PIPING ENGINEERING & DESIGN
Project Name & No:
By: |  |  |  | DCN Type: |  | Change Order
Date: | [5 empty] | Trend
General Description:
Part A - Definition
SCOPE
CAUSE
Part B - IMPACT
Op. | Act. | Group/Activity | Description of added work |  |  | Hrs per (1) | Totals
251 | A | PME Supervision
251 | B | PME Proj. Desig Basis
251 | C | PME Preliminary Design
251 | D | PME Detailed Design
251 | E | PME Deliverables |  |  |  |  | 0
252 | A | PDG Supervision
252 | B | PDG Proj. Desig Basis
252 | C | PDG Preliminary Design
252 | D | PDG Detailed Design
252 | E | PDG Deliverables
252 | F | PDG CADD Coord. |  |  |  |  | 0
253 | A | PMC Supervision
253 | B | PMC Proj. Desig Basis
253 | C | PMC Preliminary Design
253 | D | PMC Detailed Design
253 | E | PMC Deliverables |  |  |  |  | 0
254 | A | PSE Supervision
254 | B | PSE Proj. Desig Basis
254 | C | PSE Preliminary Design
254 | D | PSE Detailed Design
254 | E | PSEDeliverables |  |  |  |  | 0
250 | A | PEL Supervision
250 | B | PEL Proj. Desig Basis
250 | C | PEL Preliminary Design
250 | D | PEL Detailed Design
250 | E | PEL Deliverables |  |  |  |  | 0
0
0
When "X" is inserted in this box see note (2) - |  |  |  |  | Total Labor Hours: |  | 0
DCN DETERMINATION
DCN Action: |  |  | DCN Approved, Proceed: |  | Comment
|  |  | DCN Revise and Resubmit: |  | Comment
|  |  | DCN Rejected: |  | Comment
|  |  | DCN Cancelled: |  | Comment
Entity |  |  |  | SIGNATURE |  |  | DATE
Piping Department
Project Management
Client Management
(1) - "Hours per" includes: Document development, extraction, editing, corrections, review, approvals and printing.
(2) - When noted ("X") all hours for this DCN will be added to Estmate. and CLS even if "Rejected."

## SAMPLE DCN LOG
PIPING ENGINEERING & DESIGN "DCN" LOG
| Project No. |  |  | Project Name | PEL |  |  |  | Piping Manager |  | Project Manager |  | Client
| 2011-106 |  |  | Temple Refinery Upgrade | A. R. Tennyson |  |  |  | A. G. Patterson |  | Al. Demming |  | G. R. Southerland
| Current Totals: | [7 empty] | 1022 | 160 | 0 | 160 | 1022 | 0
| DCN No. | DCN Type |  | General Description | Status |  |  |  | Proposed Hours |  | Rejected Hours |  | Approved Hours
|  | C. O. | TREND |  | Submitted | Approved | Rejected | Cancelled | C. O. | Trend | C. O. | Trend | C. O. | Trend
Sample Data | 50-001 | X |  | New Feed and Product Storage Tanks addad | X | X |  |  | 572 |  |  |  | 572
Sample Data | 50-002 | X |  | Client addition, Feed Coalessor | X | X |  |  | 450 |  |  |  | 450
Sample Data | 50-003 |  | X | Vendor late equipment change | X |  | X |  |  | 160 |  | 160

## DCN LOG
PIPING ENGINEERING & DESIGN "DCN" LOG
Project No. |  |  | Project Name | PEL |  |  |  | Piping Manager |  | Project Manager |  | Client
Current Totals: | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
DCN No. | DCN Type |  | General Description | Status |  |  |  | Proposed Hours |  | Rejected Hours |  | Approved Hours
| C. O. | TREND |  | Submitted | Approved | Rejected | Cancelled | C. O. | Trend | C. O. | Trend | C. O. | Trend
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0