## Guidelines
Process Plant Equipment Layout and Design Guides
Guidelines for use:
At the start of detailed design, a designer is assigned an an area of work by the responsible supervisor. The supervisor then sits down with the assigned designer and reviews each item on the list for each type of equipment contained in the area. The review can be done on a hard copy or on an electronic copy. Between the supervisor and the designer they review the sheet against the expected piece of equipment. Together, they place a "Y" (for yes) or a "N" (for no) in the column marked "Applicable" for each listed item. This then becomes only the minimum requirement for active consideration during the design process.
Designer
As the designer proceeds with the design work he (or she) shall place their initials & date in the "Designer Confirms" column when each item has been properly satisfied or determined to be not applicable. The completed sheet forms a part of the design development package and stays with the area records.
Checker
The checker assigned to perform the checking or QA/QC shall use this sheet and place their initials & date in the "Checker Confirms" column to varify that all the required items have been properly addressed.
Listed below are the six major issues that need to be considered as a part of the design process for every piece of equipment. These sheets currently exist for only the most common types of the major equipment found in Refinerys and Chemical Plants.
Engineering and Design Issues
This category of issues includes: What is it? Where is it? Do the reference documents and the item match? Is all the correct information available and is all the available information correct?
Manufacturing and Fabrication Issues
This category of issues includes the question of the possibility of vendor supplied supports, clearances, anchors, bracing or other items. It also deals with clearance accesses for pipe routing to and from piping connections.
Construction and Installation Issues
This category of issues includes how the equipment item is going to be installed and what, if any, it will have on the location of the equipment and/or the piping.
Operational Issues
This category of issues includes accessibility to operational valves and instruments.
Maintenance Issues
This category of issues includes the accessibility to areas of the equipment that require maintenance.
Safety Issues
This category of issues includes the requirement for relief valves, rapid and unrestricted egress, Fireproofing, safety (personnel protection) insulation or safety showers.

## Blank Form
Process Plant Equipment Layout & Design Guide
(Define)
Basic description:
Primary function:
Key Performance Issues:
Equipment Number : |  | (Define)
Description of Layout consideration | Source | Applicable Y/N | Designer Confirm | Checker Confirm
A -- Engineering and Design Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
B -- Manufacturing and Fabrication Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
C -- Shipping and Traffic Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
D -- Construction and Installation Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
E -- Operational Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
F -- Maintenance Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
G -- Safety Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Safety Device (PSV, Thermal Relief, Rupture Disk) | P&ID
Uninsulated skin temperature (Personnel Protection) | Datasheet

## Centrif Pump.
Process Plant Equipment Layout & Design Guide
Centrifugal Pump (API Type)
Basic description: May be small, medium or large. Will normally be specified in pairs. May have top or end suction. Will normally have top discharge. This version is manufactured with the shaft in the horizontal position. The driver may be motor, turbine or engine.
Primary function: Used to transfer a liquid commodity from one point to another. May be called Charge Pumps, Transfer Pumps, Loading Pumps or any other designation depending on function.
Key Performance Issues: Proper sizing (head), location relationship to the suction source related equipment, correct suction and discharge piping configuration, proper operation, and prudent maintenance.
Equipment Number : |  | Centrifugal Pump
Description of Layout consideration | Source | Applicable Y/N | Designer Confirm | Checker Confirm
A -- Engineering and Design Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
System location, schematic | P&ID
Equipment configuration matches P&ID | P&ID & Outline
Number of units and designation | P&ID/Eqp. datasheet
Physical location, horizontal & elevation | LCP
Operating Pressure/Temperature | Equip. Datasheet
Suction Nozzle orientation | P&ID/Eqp. datasheet
Suction Nozzle data (Size, Rating, Facing) | P&ID/Eqp. datasheet
Discharge Nozzle orientation | P&ID/Eqp. datasheet
Discharge Nozzle data (Size, Rating, Facing) | P&ID/Eqp. datasheet
Secondary Nozzles (Vents, Drains, PI,) | P&ID/Eqp. datasheet
Insulation, Type, thickness, and clearances | P&ID/Eqp. datasheet
Nozzle location dimensions | Equip. Outline
Nozzle clearance between Suct./ Disch. pipe flg. O. D. | Equip. Outline
Nozzle ID matches pipe ID (Require taper bore?) | Outline & Pipe Spec
Centerline shaft/centerline base plate dimension | Equip. Outline
Base plate anchor bolt Locations | Equip. Outline
Base Plate Thickness given | Equip. Outline
Operating weight | Equip. Outline
Hydro test weight (Full of water) | Equip. Outline
B -- Manufacturing and Fabrication Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Vendor furnished piping located and supported | Equip. Outline
Driver - Frame Type, Size, Dimensions | Equip. Outline
C -- Construction and Installation Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Overall Size | Equip. Outline
Foundation (or Pad) overall size and elevation | Struct Dwg.
Dry Installation Weight (Empty weight) | Equip. Outline
Overhead clearance | Layout
D -- Operational Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Inlet and outlet piping configuration (Critical) | P&ID
Inlet and Outlet block valve accessibility | Design Spec
Accessibility to local Instruments (TI, PI, etc.) | Designer
Visibility of local Instruments (TI, PI, etc.) | Designer
Accessability to Elect. Start/Stop push-button station | Designer
E -- Maintenance Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Overhead clear for motor and pump removal | Designer
Coupling and seal area clear for access | Designer
F -- Safety Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Safety Device (PSV, Thermal Relief, Rupture Disk) | P&ID
Uninsulated skin temperature (Personnel Protection) | Datasheet

## Fin Fan
Process Plant Equipment Layout & Design Guide
Fin Fan (Air Cooled) Type Exchanger
Basic description: Small, medium and large forced draft or induced draft Air cooled Exchangers. Forced Draft units have the motor and the fan under the tube bundle and blow the air up past the tubes. Induced Draft units may have the motor under the tubes or above the tubes but will have the fan above the tubes and suck the air up past the tubes. Fin Fans will have one or two tube bundles per unit. Some installations may require ten or more units per service. Units will normally have two Fans per unit (Small package units may have only one fan). Most Fin Fans normally have only one inlet and one outlet per tube bundle, however some may have two inlets and two outlets per bundle. Some are totally open-sided and some have full side panels. Some may also come with steam coils to temper the air in fridged climates.
Primary function: Used for cooling of process or utility gas streams where Cooling water is in short supply. May be called a Cooler or Condenser.
Key Performance Issues: Proper sizing (duty), location relationship to related equipment, correct inlet and outlet piping configuration, clean operation, and prudent maintenance.
Equipment Number : |  | Fin Fan
Description of Layout consideration | Source | Applicable Y/N | 7 | Checker Confirm
A -- Engineering and Design Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
System location, schematic | P&ID & Plot Plan
Unit, Cell, Tube Bundle configuration (P&ID Vs. Outline) | P&ID & Outline
Physical location, horizontal & elevation | LCP & Plot Plan
Number of (Tube) passes (Odd or Even) | Equip. Datasheet
Number of Passes (odd or even) | Equip. Datasheet
Requirement for sloping tubes (Free Drainage) | P&ID
Location of upstream equipment relative to inlet | Layout
Location of downstream equipment relative to outlet | Layout
Design/Operating Temperature & Pressure | Equip. Datasheet
Key column location & orientation (North Arrow) | LCP
Inlet header pipe expansion | Designer calc.
Cell or Unit spacing (separation for pipe supt.) | Designer calc.
Inlet Nozzle count (Tube bundle inlet header) | P&ID/Eqp. datasheet
Inlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp. datasheet
Outlet Nozzle count (Tube bundle outlet header) | P&ID/Eqp. datasheet
Outlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp. datasheet
Inlet Nozzle Orientation | Equip outline
Inlet Nozzle location dimensions | Equip outline
Outlet Nozzle Orientation | Equip outline
Outlet Nozzle location dimensions | P&ID/Eqp. datasheet
Supplementary Heat coil Inlet data (Size, rating, Facing) | P&ID & Equip outline
Heat coil Inlet location dimensions | Equip outline
Supplementary Heat coil Outlet data (Size, rating, Facing) | Equip outline
Heat coil Outlet location dimensions | Equip outline
Nozzle Loading | Designer/Stress
Winterization Dampers (location, spacing, dimensions) | Equip. Outline
Secondary Nozzles (Vents, Drains, PI, TI, Chem. Clean) | P&ID/Eqp. datasheet
Nozzle projections | Equip. Outline
Special Nozzle configuration (Elbow, tangential, etc.) | Designer
Nozzle clearance between OD Flange & support steel | Designer
Nozzle ID matches pipe ID (Require taper bore?) | Outline & Pipe Spec
Establish Pipe Support reqmts | Designer
Integral Pipe Supt w/ Exchanger Support structure | Designer
Support Leg Locations | Designer
Transverse carrier beams provided (Module design) | Equip. Outline
Integral grating platforms provided (Under all units) | Equip. Outline
Platform for Fan motor level | Equip. Outline
Minimum head room for platform at fan motors | Design criteria
Platforms w/ ladders provided to inlet header box | Equip. Outline
Platforms w/ ladders provided to outlet header box | Equip. Outline
Air control Louver reqmts (location, spacing, dimensions) | Equip. Outline
Wind and Seismic requirements | Structural
Vibration sensors required | Datasheet
Shipping Stops required for Tube Bundles | Vendor
Shipping Braces Required for Module or Package Units | Vendor
Operating weight | Equip. Outline
Hydro test weight (Full of water) | Equip. Outline
B -- Manufacturing and Fabrication Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
PWHT (Post Weld Heat Treat) Required | Equip. Outline
Code Name Plate each cell (Orientation & Location) | Designer
Paint or Galvanizing | Equip. Outline
Special cleaning | Equip. Outline
C -- Shipping and Traffic Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Overall size is shippable with full shop assembly | Vendor & Traffic
Special shipping is required if full shop assembly | Vendor & Traffic
D -- Construction and Installation Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Overall Size | Equip. Outline
Dry Installation Weight (Empty weight) | Equip. Outline
Overhead clearance | Layout
Lifting lugs provided | Equip. Outline
Maximum Hydro test Pressure (Tubes & Header Box) | Equip. Outline
Removal of Shipping Stops | Equip. Outline
Removal of Shipping Braces | Equip. Outline
E -- Operational Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Tube side design and operating conditions | P&ID/Datasheet
Winterization protection | Equip. Spec
Inlet and outlet piping configuration (Critical) | P&ID
Inlet and Outlet block valve accessibility | Design Spec
Accessibility to local Instruments (TI, PI, etc.) | Designer
Visibility of local Instruments (TI, PI, etc.) | Designer
Hot Air Discharge | Designer
F -- Maintenance Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Header Box cover or plug access and removal | Outline & Layout
Tube rodding or cleaning | Outline & Layout
Fan access and blade removal | Outline & Layout
Motor access and removal | Outline & Layout
G -- Safety Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Safety Device (PSV, Thermal Relief, Rupture Disk) | P&ID
Uninsulated skin temperature (Personnel Protection) | Datasheet
Emergency egress | OSHA & Design Spec
Grounding Lug provided | Outline
Fireproofing of support structure (Verify clearance) | Structural Dwgs
Water Spray/Deluges System | Design Criteria

## S&T Exch
Process Plant Equipment Layout & Design Guide
Horizontal Shell And Tube Exchanger
Basic description: Large diameter outer shell of a consistent diameter with removable or non-removable tubes. Will have one or more inlets and outlets on the shell side. Will normally have only one inlet and one outlet on the tube side. This version is normally mounted in the horizontal position. This item may be mounted as a single item of equipment or stacked (multiple shells) for the same service or different services.
Primary function: Used for heating or cooling of a process or utility gas or liquid. May be called Heater, Cooler, Condenser, or Reboiler.
Key Performance Issues: Proper sizing (duty), location relationship to related equipment, correct inlet and outlet piping configuration, clean operation, and prudent maintenance.
Equipment Number : |  | S & T Exchanger
Description of Layout consideration | Source | Applicable Y/N | 7 | Checker Confirm
A -- Engineering and Design Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
System location, schematic | P&ID
Shell & Channel flow pattern (P&ID matches Outline) | P&ID & Outline
Physical location, horizontal & elevation | LCP
Shell Stacking arrangement & placement | P&ID & Datasheet
Operating Temperature | Equip. Datasheet
Anchor saddle location | LCP
Shell expansion (Radial and Longitudinal) | Designer calc.
Sliding Saddle slot size | Designer calc.
Shell Inlet Nozzle count | P&ID/Eqp datasheet
Shell Inlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp datasheet
Shell outlet Nozzle count | P&ID/Eqp datasheet
Shell outlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp datasheet
Shell Nozzle Orientation | Equip outline
Shell Nozzle Location | Equip outline
Channel Inlet Nozzle count | P&ID/Eqp datasheet
Channel Inlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp datasheet
Channel outlet Nozzle count | P&ID/Eqp datasheet
Channel outlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp datasheet
Channel Nozzle Orientation | Equip outline
Channel Nozzle Location | Equip outline
Secondary Nozzles (Vents, Drains, PI, TI, Chem. Clean) | Project. Specs
Insulation, Type, thickness, and clearances | P&ID/Eqp datasheet
Nozzle projections | Equip. Outline
Special Nozzle configuration (Elbow, tangential, etc.) | Designer
Nozzle clearance between Flange OD & Foundation | Designer
Nozzle ID matches pipe ID (Require taper bore?) | Outline & Pipe Spec
Integral Pipe Supt w/ Exchanger Foundation | Designer
Support Locations | Designer
Support/Foundation height, weidth | Struct. Dwg.
Saddle projections | Equip. Outline
Saddle Base Plate Thickness | Equip. Outline
Location of Anchor Saddle Bolt Holes | Equip. Outline
Size of Anchor Saddle Bolt Holes | Equip. Outline
Location of Sliding Saddle Bolt Slots | Equip. Outline
Operating weight | Equip. Outline
Hydro test weight (Full of water) | Equip. Outline
B -- Manufacturing and Fabrication Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Clearance between Nozzle. Repads & Shell Welds | Designer
PWHT (Post Weld Heat Treat) Required | Equip. Outline
Code Name Plate (Orientation & Location) | Designer
C -- Construction and Installation Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Overall Size | Equip. Outline
Dry Installation Weight (Empty weight) | Equip. Outline
Overhead clearance | Layout
Maximum Hydro test Pressure (Shell) | Equip. Outline
Maximum Hydro test Pressure (Tubes) | Equip. Outline
Minimum Hydro test Temperature (Shell) | Equip. Outline
Minimum Hydro test Temperature (Tubes) | Equip. Outline
Maximum Differential Hydro test Pressure (Shell/Tube) | Equip. Outline
D -- Operational Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Shell side design and operating conditions | P&ID/Eqp datasheet
Tube side design and operating conditions | P&ID/Eqp datasheet
Inlet and outlet piping configuration | Co. Design Guide
Inlet and Outlet block valve accessibility | Co. Design Guide
Accessibility to local Instruments (TI, PI, etc.) | Designer
Visibility of local Instruments (TI, PI, etc.) | Designer
E -- Maintenance Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Channel removal method & clearance | Project. Specs.
Channel removal Lifting Lugs | Exch. outline
Shell Cover removal method & clearance | Project. Specs.
Shell Cover removal Lifting Lugs | Exch. outline
Tubes Fixed or Removable | Datasheet
Tube Bundle removal method | Project. Specs.
Tube Bundle removal space | Exch. outline
Tube Bundle weight | Exch. outline
Tube Bundle Pull Points (Dead Men) | Project. Specs.
Stud Tentioners (Space & Access) | Designer
F -- Safety Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Safety Device (PSV, Thermal Relief, Rupture Disk) | P&ID
Uninsulated skin temperature (Personnel Protection) | Datasheet

## Horiz. Reboil.
Process Plant Equipment Layout & Design Guide
Kettle Type Reboiler
Basic description: Large diameter outer shell with eccentric cone transition to smaller diameter removable tube bundle. Will normally have one inlet and one outlet on the tube side. May have one or two main liquid inlet located on the bottom of the shell side. May have one or two vapor outlets located on the top of the shell. May have multiple level instrument connections on the shell to monitor the liquid level in the shell.
Primary function: Used for heating a process liquid in the bottom section of a vertical vessel (tower). May be called Heater or Reboiler.
Key Performance Issues: Proper sizing (duty), location relationship to the liquid level in the tower, liquid/vapor hydraulics, correct inlet and outlet piping configuration, clean operation, and prudent maintenance.
Equipment Number : |  | Kettle Type Reboiler
Description of Layout consideration | Source | Applicable Y/N | Designer Confirm | Checker Confirm
A -- Engineering and Design Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>>
System location, schematic | P&ID
Shell & Channel flow pattern (P&ID matches Outline) | P&ID & Outline
Physical location, horizontal & elevation | LCP & P&ID
Shell weir elevation relationship | P&ID & Eqp Datasht
Operating Temperature | Equip. Datasheet
Anchor support location | Designer Calc
Shell expansion (Radial and Longitudinal) | Designer calc.
Shell Inlet Nozzle count | P&ID & Eqp Datasht
Shell Inlet Nozzle data (Size, Rating, Facing) | P&ID & Eqp Datasht
Shell outlet Nozzle count | P&ID & Eqp Datasht
Shell outlet Nozzle data (Size, Rating, Facing) | P&ID & Eqp Datasht
Shell Nozzle Orientation | Equip outline
Shell Nozzle location dimensions | Equip outline
Channel Inlet Nozzle configuration & orientation | P&ID & Eqp Datasht
Channel Inlet Nozzle data (Size, Rating, Facing) | P&ID & Eqp Datasht
Channel outlet Nozzle configuration & orientation | P&ID & Eqp Datasht
Channel outlet Nozzle data (Size, Rating, Facing) | P&ID & Eqp Datasht
Channel Nozzle location dimensions | Equip outline
Secondary Nozzles for Vents, Drains, PI & TI | Project. Specs
Secondary Nozzles for Chem. Cleaning | Project. Specs
Insulation, Type, thickness, and clearances | P&ID & Eqp Datasht
Nozzle projections | Equip. Outline
Special Nozzle configuration (Elbow, tangential, etc.) | Designer
Nozzle clearance between O. D. Flange & support | Designer
Nozzle ID matches pipe ID (Require taper bore?) | Outline & Pipe Spec
Integral Pipe Supt w/ Exchanger support | Designer
Support saddle Locations | Designer
Support saddle projections | Equip. Outline
Support Base Plate Thickness | Equip. Outline
Location of Anchor Saddle bolt holes | Designer determine
Size of Anchor Saddle bolt holes | Equip. Outline
Location of sliding saddle slots | Designer determine
Size of sliding saddle slots | Equip. Outline
Operating weight | Equip. Outline
Hydro test weight (Full of water) | Equip. Outline
B -- Manufacturing and Fabrication Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>>
Clearance between Nozzle. Repads & Shell Welds | Designer
PWHT (Post Weld Heat Treat) Required | Equip. Outline
Code Name Plate (Orientation & Location) | Designer
C -- Construction and Installation Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>> | >>>>>>>>
Overall Size | Equip. Outline
Dry Installation Weight (Empty weight) | Equip. Outline
Overhead clearance | Layout
Maximum Hydro test Pressure (Shell) | Equip. Outline
Maximum Hydro test Pressure (Tubes) | Equip. Outline
Minimum Hydro test Temperature (Shell) | Equip. Outline
Minimum Hydro test Temperature (Tubes) | Equip. Outline
Maximum Differential Hydro test Pressure (Shell/Tube) | Equip. Outline
D -- Operational Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>> | >>>>>>>>
Shell side design and operating conditions | P&ID/Datasheet
Tube side design and operating conditions | P&ID/Datasheet
Inlet and outlet piping configuration | Co. Design Guides
Inlet and Outlet block valve accessibility | Co. Design Guides
Accessibility to local Instruments (TI, PI, etc.) | Designer
Visibility of local Instruments (TI, PI, etc.) | Designer
E -- Maintenance Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>> | >>>>>>>>
Channel removal method & clearance | Project. Specs.
Channel removal Lifting Lugs | Exch. outline
Tube Bundle removal method | Project. Specs.
Tube Bundle removal space | Exch. outline
Tube Bundle weight | Exch. outline
Stud Tentioners (Space & Access) | Designer
F -- Safety Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>>
Safety Device (PSV, Thermal Relief, Rupture Disk) | P&ID
Uninsulated skin temperature (Personnel Protection) | Datasheet

## Vert. Reboil
Process Plant Equipment Layout & Design Guide
Thermosyphon Reboiler (Vertical) Type Exchanger
Basic description: Large diameter outer shell with removable or non-removable tubes. Will normally have one inlet and one outlets on the shell side. Will normally have only one inlet and one outlet on the tube side. This version is mounted in the vertical position on the side of a vertical vessel or on supports along side a vertical vessel.
Primary function: Used for heating a process liquid in the bottom section of a vertical vessel (tower). May be called Heater or Reboiler.
Key Performance Issues: Proper sizing (duty), location in relationship to the liquid level in the tower, liquid/vapor hydraulics, correct inlet and outlet piping configuration, clean operation, and prudent maintenance.
Equipment Number : |  | Thermosyphon Reboiler
Description of Layout consideration | Source | Applicable Y/N | Designer Confirm | Checker Confirm
A -- Engineering and Design Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
System location, schematic | P&ID/Plot Plan
Shell & Channel flow pattern (P&ID matches Outline) | P&ID & Outline
Physical location, horizontal & elevation | LCP & P&ID
Operating Temperature | Equip. Datasheet
Primary support location | Designer Calc
Shell expansion (Radial and Longitudinal) | Designer calc.
Shell Inlet Nozzle count | P&ID/Eqp datasheet
Shell Inlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp datasheet
Shell outlet Nozzle count | P&ID/Eqp datasheet
Shell outlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp datasheet
Shell Nozzle Orientation | Equip outline
Shell Nozzle location dimensions | Equip outline
Channel Inlet Nozzle configuration & orientation | P&ID/Eqp datasheet
Channel Inlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp datasheet
Channel outlet Nozzle configuration & orientation | P&ID/Eqp datasheet
Channel outlet Nozzle data (Size, Rating, Facing) | P&ID/Eqp datasheet
Channel Nozzle location dimensions | Equip outline
Channel Nozzle locations match Vessel or Tower | Vess. & Equip outline
Secondary Nozzles (Vents, Drains, PI, TI, Chem. Clean) | P&ID/Eqp datasheet
Insulation, Type, thickness, and clearances | P&ID/Eqp datasheet
Nozzle projections | Equip. Outline
Special Nozzle configuration (Elbow, tangential, etc.) | Designer
Nozzle clearance between Flange OD & support | Designer
Nozzle ID matches pipe ID (Require taper bore?) | Outline & Pipe Spec
Integral Platform Supt w/ Exchanger support | Designer
Support Lug Locations | Designer
Support Lug projections | Equip. Outline
Saddle Base Plate Thickness | Equip. Outline
Operating weight | Equip. Outline
Hydro test weight (Full of water) | Equip. Outline
B -- Manufacturing and Fabrication Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Clearance between Nozzle. Repads & Shell Welds | Designer
PWHT (Post Weld Heat Treat) Required | Equip. Outline
Code Name Plate (Orientation & Location) | Designer
C -- Construction and Installation Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Overall Size | Equip. Outline
Dry Installation Weight (Empty weight) | Equip. Outline
Overhead clearance | Layout
Maximum Hydro test Pressure (Shell) | Equip. Outline
Maximum Hydro test Pressure (Tubes) | Equip. Outline
Minimum Hydro test Temperature (Shell) | Equip. Outline
Minimum Hydro test Temperature (Tubes) | Equip. Outline
Maximum Differential Hydro test Pressure (Shell/Tube) | Equip. Outline
D -- Operational Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Shell side design and operating conditions | P&ID/Eqp datasheet
Tube side design and operating conditions | P&ID/Eqp datasheet
Inlet and outlet piping configuration | Co. Design Guides
Inlet and Outlet block valve accessibility | Co. Design Guides
Accessibility to local Instruments (TI, PI, etc.) | Designer
Visibility of local Instruments (TI, PI, etc.) | Designer
E -- Maintenance Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Channel removal method & clearance | Project. Specs.
Channel removal Lifting Lugs | Exch. outline
Shell Cover removal method & clearance | Project. Specs.
Shell Cover removal Lifting Lugs | Exch. outline
Tubes Fixed or Removable | Datasheet
Tube Bundle removal method | Project. Specs.
Tube Bundle removal space | Exch. outline
Tube Bundle weight | Exch. outline
Stud Tentioners (Space & Access) | Designer
F -- Safety Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Safety Device (PSV, Thermal Relief, Rupture Disk) | P&ID
Uninsulated skin temperature (Personnel Protection) | Datasheet

## Horiz. Vess.
Process Plant Equipment Layout & Design Guide
Horizontal Vessel (Accumulator)
Basic description: Medium to large diameter horizontal vessel with or without a boot. Will normally have one primary inlet. May have multiple liquid and vapor outlets. Will have multiple nozzles for level, pressure, and temperature instrumentation along with one or more nozzles for vents, drains and relief valves. These vessels will also have one or more manholes and steam-out connections.
Primary function: Used as a holding and seperation point in a process or utility stream. May be called Accumulator, Receiver, or Surge Drum.
Key Performance Issues: Proper sizing (Volume), location relationship to related equipment, correct inlet and outlet nozzle locations, correct inlet and outlet piping configuration, proper instrument location and proper operation.
Equipment Number : |  | Horizontal Vessel
Description of Layout consideration | Source | Applicable Y/N | Designer Confirm | Checker Confirm
A -- Engineering and Design Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>>
System location, schematic | P&ID
Vessel size and shape (P&ID matches Outline) | P&ID & Outline
Physical location, horizontal & elevation | P&ID and LCP
Plant orientation noted on vess. (North/South/East/West) | LCP
Operating Temperature (Use Temp of inlet line) | Equip. Datasheet
Vessel shell expansion (Radial and Longitudinal) | Designer calc.
Anchor saddle location | LCP
Saddle projections | Equip. Outline
Saddle Base Plate Thickness | Equip. Outline
Location of Anchor Saddle Bolt Holes | Equip. Outline
Size of Anchor Saddle Bolt Holes | Equip. Outline
Location of Sliding Saddle Bolt Slots | Equip. Outline
Sliding Saddle slot size | Designer calc.
Vessel Nozzle count | P&ID/Eqp. datasheet
Vessel nozzle designations and purpose | P&ID/Eqp. datasheet
Nozzle data (Size, Rating, Facing) | P&ID/Eqp. datasheet
Nozzle projections | Equip. Outline
Manhole count criteria | Proj. & Vess Spec.
Manhole size | Proj. & Vess Spec.
Manhole cover handling criteria (Davit, hinge, etc.) | Proj. & Vess Spec.
Manhole locations | Equip. Outline
Boot size (Diameter & length) | Equip. Outline
Boot location | Equip. Outline
Vessel internals defined | Equip. Outline
Vortex breaker defined | Equip. Outline
Insulation, Type, thickness, and clearances | P&ID/Eqp. datasheet
Top nozzle require extention to clear platform | Designer
Platform clips required & Defined | Designer
Special Nozzle configuration (Elbow, tangential, etc.) | Designer
Nozzle clearance between Flange OD & Foundation | Designer
Nozzle ID matches pipe ID (Require taper bore?) | Outline & Pipe Spec
Integral Pipe Supt w/ Vessel Foundation | Designer
Vessel Support Locations | Designer
Aessel Support/Pier Size, Location, Height
Operating weight | Equip. Outline
Hydrotest weight (Full of water) | Equip. Outline
B -- Manufacturing and Fabrication Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Clearance between Nozz. Repads & Shell Welds | Designer
PWHT (Post Weld Heat Treat) Required | Equip. Outline
Code Name Plate (Orientation & Location) | Designer
C -- Construction and Installation Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Overall Size | Equip. Outline
Dry Installation Weight (Empty weight) | Equip. Outline
Overhead clearance | Layout
Maximum Hydrotest Pressure | Equip. Outline
D -- Operational Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Normal design and operating conditions | P&ID/Datasheet
Inlet and outlet piping configuration | Co. Design Guides
Inlet and Outlet block valve accessibility | Co. Design Guides
Accessibility to local Instruments (TI, PI, etc.) | Designer
Visibility of local Instruments (TI, PI, etc.) | Designer
E -- Maintenance Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Manhole access | Co. Design Guides
Internal access (internal ladder required?) | Co. Design Guides
F -- Safety Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>>>> | >>>>>>>>>>
Safety Device (PSV, Rupture Disk) | P&ID
Uninsulated skin temperature (Personnel Protection) | Datasheet

## Vert. Vess.
Process Plant Equipment Layout & Design Guide
Vertical Trayed Vessel (Fractionation Column or Tower)
Basic description: Medium to large diameter vertical vessel with tray type internals. Will normally have one primary feed nozzle. The line attached to this nozzle will be liquid or mixed phase flow. Will normally have only one vapor outlet located on the top vessel head or on the shell near the top. This vessel will normally have only one primary or main feed inlet. This vessel will normally operate at a high temperature and therefore will expand vertically in perportion to the operation temp. and the materials of construction. This type of equipment will have many piping lines that connect to it and therefore will travel up and down the vessel sides. These lines will also need supports and guides.
Primary function: Separation of one or more products from the primary feed stream. .
Key Performance Issues: Proper sizing (Volume), number & type of trays, location relationship to related equipment, correct inlet and outlet nozzle to tray locations, correct inlet and outlet piping configuration, proper instrument location and proper operation.
Equipment Number : |  | Vertical Vessel
Description of Layout consideration | Source | Applicable Y/N | Designer Confirm | Checker Confirm
A -- Engineering and Design Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
System location, schematic | P&ID
Vessel size and shape (P&ID matches Outline) | P&ID & Outline
Physical location, horizontal & elevation | P&ID and LCP
Vessel Foundation (Location, Top of Grout) | Structural Drawing
Compass orient noted on vessel. head (North, South, etc.) | LCP
Vessel Design & Operating Temperature | Equip. Datasheet
Number of Trays | P&ID/Eqp. Datasheet
Number of Tray passes | P&ID/Eqp. Datasheet
Type of Trays | P&ID/Eqp. Datasheet
Tray Spacing | P&ID/datasheet
Operating Temperature of connected lines | Line List
Vessel shell expansion (Radial and Longitudinal) | Designer calc.
Vessel Nozzle count matches P&ID | P&ID/Eqp. Datasheet
Vessel nozzle designations and purpose | P&ID/Eqp. Datasheet
Nozzle data (Size, Rating, Facing) | P&ID/Eqp. Datasheet
Nozzle projections | Equip. Outline
Manhole count and criteria | Proj. & Vessel Spec.
Manhole size | Proj. & Vessel Spec.
Manhole cover handling criteria (Davit, hinge, etc.) | Proj. & Vessel Spec.
Manhole locations | Equip. Outline
Liquid level criteria defined (LLL, LLN, LLH, etc.) | P&ID/Eqp. Datasheet
PI, TI Criteria defined | P&ID/Eqp. Datasheet
Vessel internals defined | Equip. Outline
Vortex breaker defined | Equip. Outline
Insulation, Type, thickness, and clearances | P&ID/datasheet
Top nozzle require extension to clear platform | Designer
Platform clips required? (Defined) | Designer
Special Nozzle configuration (Elbow, tangential, etc.) | Designer
Nozzle clearance between O. D. Flange Platform | Designer
Nozzle ID matches pipe ID (Require taper bore?) | Outline & Pipe Spec
Pipe Support sized and located for all lines | Designer
Pipe Guides sized and located for all lines | Designer
Platform cut-outs sized and located for all lines | Designer
Base Plate "Chair" height | Equip. Outline
Platforms defined (width, orient., elevation, I. D.) | Designer
Ladders defined (I. D., location, length, cage) | Designer
Davit defined (Height, capacity, location, etc.) | Designer
Operating weight | Equip. Outline
Hydro test weight (Full of water) | Equip. Outline
B -- Manufacturing and Fabrication Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Clearance between Nozzle. Reinforcing pads & Shell Welds | Designer
PWHT (Post Weld Heat Treat) Required | Equip. Outline
Code Name Plate (Orientation & Location) | Designer
C -- Construction and Installation Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Overall Size | Equip. Outline
Dry Installation Weight (Empty weight) | Equip. Outline
Overhead clearance | Layout
Maximum Hydro test Pressure | Equip. Outline
Type, size, and location of top lifting lugs | Equip. Outline
Type, size, and location of tail lifting lugs | Equip. Outline
D -- Operational Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Normal design and operating conditions | P&ID/Datasheet
Inlet and outlet piping configuration | Co. Design Guides
Inlet and Outlet block valve accessibility | Co. Design Guides
Accessibility to local Instruments (TI, PI, etc.) | Designer
Visibility of local Instruments (TI, PI, etc.) | Designer
E -- Maintenance Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Manhole access | Co. Design Guides
Internal access (internal ladder required?) | Co. Design Guides
F -- Safety Issues | >>>>>>>>>>>>>> | >>>>>>>> | >>>>>>> | >>>>>>>
Safety Device (PSV, Rupture Disk) | P&ID
Uninsulated skin temperature (Personnel Protection) | Datasheet