## Sheet1
Title
User Advisory - This Excel Worksheet or Workbook "Tool" is locked and password protected. The user may only enter date in the "yellow" cells. Other cells on this "Tool" includes locked "cells" that contain complex math formulas. Care should be taken to learn where these cells are and if the streadsheet is ever unlocked that the cells with the formulas are not disturbed. Disturbing or altering these cells may render the "Tool" unable to function properly.
Instruction # 1
Instruction # 2
Instruction # 3
Instruction # 4
Instruction # 5
Instruction # 6
Instruction # 7
Instruction # 8
Instruction # 9
Instruction # 10
Instruction # 11
Instruction # 12
Instruction # 13

## Chart
PROJECT KICKOFF | [6 empty] | 1 | Preliminary Engineering | [5 empty] | 2 | Preliminary Engineering |  |  |  |  | 3 | Scope, Estimate & Schedule | [5 empty] | 4 | Detailed Engineering and Design |  |  |  | 5 | Detailed Engineering and Design |  |  |  |  | 6 | Production Engineering |  |  |  |  | 7 | Project Completion (Home Office) |  |  |  | 8 | Fabrication & Delivery |  |  | 9 | Construction |  |  | 10
CLIENT | Client and Company PM jointly set time, place and agenda for Kickoff meeting |  |  |  | Joint Company and Client Project Kick-Off meetings
Project Mngmt. |  |  |  | Arrange for project number and space, office & computers
En'g Mngmt |  | Engr Mngr Selected
Process |  |  | Discipline Leads assigned | [6 empty] | PFD & Line Data available | [6 empty] | P&IDs IFA |  |  | P&IDs IFD |  | Util P&IDs
Civil
Structural
Mech Equip | [22 empty] | 1 st Vendor Drawings
Vessels | [30 empty] | Vess Orient Review
Electrical
Instruments
Piping Material Engineering | [10 empty] | PME assigned (Latest) | Piping Line Class Specs |  |  | Piping Line Class Specs | [5 empty] | Ln. Cl. Specs Complete | [16 empty] | De-staff PME Staff as needed
Prepare other Specs (Insulation, Paint, Hydrotest, etc)
[16 empty] | P&ID Reviews |  |  |  |  | Prepare "Specialty" Item List and Specifications | [6 empty] | Build Commodity Code Catalog
[45 empty] | Prepare input to Piping Final Job Report | [5 empty] | De-staff PME Lead
[15 empty] | Line Number and "Spec" P&IDs | [5 empty] | Scope of Work, Labor Hour Estimate & input to Piping Control Level Schedule |  |  |  | Build 3D Data Base for Model | [13 empty] | Answer questions as required during Iso Check and Issue
[15 empty] | Initiate Line List | [7 empty] | Update Line List for Utility | [15 empty] | Lead Piping Material Engineer available as required | [5 empty] | Lead Piping Material Engineer available as required |  |  |  |  | Lead Piping Material Engineer available as required
Piping Design Group | [13 empty] | Piping Design Supervisor assigned (latest) | Develop Plot Plan |  |  | Plot Plan Issued for In-house review | Resolve comments | Plot Plan IFA | [7 empty] | Detailed Vessel Orientation |  |  | Vessel Orientation Review |  |  |  | In-house Model Review | Update as Required | Client Model Review | [13 empty] | De-staff last PDG Staff and Supervisor
[25 empty] | Preliminary MTO by sketch and other methods as appropriate | [12 empty] | Update as required | Extract all Isometrics, Check, make corrections as required. Initiate QA/QC Check of all Critical Lines in accordance with approved project plan. | [5 empty] | Check, Correct and Issue all Isometrics |  |  | De-staff non-essential staff
[15 empty] | Develop Piping Design and Layout Specification | [12 empty] | Detailed Piping Layout all Areas |  |  |  |  | Detail Piping Layout all Areas | [16 empty] | Field follow-up as required
Develop Piping Standard Details
[16 empty] | P&ID Reviews |  |  |  |  | Scope of Work, Labor Hour Estimate & input to Piping Control Level Schedule | [18 empty] | Process "Heat Tracing" Isometrics as required.
[25 empty] | Create 3D Model Partitions | [24 empty] | Prepare input to Piping Final Job Report
Piping Material Control | [14 empty] | Piping Material Control Supvr assigned (not Staffed) |  |  |  |  | All PMC Staffed | Perform "Valve" MTO as P&IDs become available | [6 empty] | Prepare RFQ for all Piping material | [5 empty] | Pipe Mat'l Bids Due | [12 empty] | MTO Final Isometrics | Update final material quantities and Check for Shortages |  |  | De-staff all PMC staff except Supervisor
[38 empty] | Download all Piping Material | Update quantities, Prepare and issue all Purchase Orders | [10 empty] | Evaluate Shortages and Issue Supplements as required.
[26 empty] | Prepare Shop Tonnage Estimate | [14 empty] | Prepare Bill of Material (BOM) for Isometrics as Issued |  |  |  | Prepare Bill of Material (BOM) for Isometrics as Issued | [6 empty] | Process Final Supplement data |  | Collect Data on all surplus Piping material and with Client resolve "Keep or Return" guidelines
P&ID Reviews
[21 empty] | Scope of Work, Labor Hour Estimate & input to Piping Control Level Schedule | [33 empty] | De-staff PMC Supervisor
[16 empty] | PMC Supervisor available as required | [33 empty] | Prepare input to Piping Final Job Report
Pipe Stress Engineering | [14 empty] | Lead Pipe Stress Eng assigned & avail as required
[37 empty] | Finalize all Stress related Engineered Items (Spring Hangers, Expansion Joints, etc.) |  | Issue all Purchase Orders for Stress related Engineered Items | [8 empty] | De-staff Pipe Stress Staff
[33 empty] | Support Piping Layout as required | [6 empty] | Support Isometric Checking and Issue as required |  |  |  |  | Support Isometric Checking and Issue as required
P&ID Reviews
[21 empty] | Scope of Work, Labor Hour Estimate & input to Piping Control Level Schedule | [24 empty] | Prepare input to Piping Final Job Report
PSE Supervisor available as required
Piping Engineering Lead (PEL) |  |  | Piping Lead assigned |  |  | Piping Lead meets with Piping Department Manager to address Preliminary Staff assignments |  | Determine availability of Group Leads | [7 empty] | P&ID Reviews | [5 empty] | Review and finalize Shop Fab Spec. |  |  | Develop Pipe Fab Shop Bidders List |  |  | Initiate Pipe Fab Shop Request For Quote | [6 empty] | Shop Fab Bids Due |  |  |  | Finalize Pipe Fab Shop Purchase Order | [7 empty] | Issue Final Iso to Shop Fab | [8 empty] | De-staff Piping Engineering Lead
|  |  |  | Attend all project meetings and collect all project data relevant to Piping |  |  |  |  | Input to overall Project Execution Plan | [12 empty] | Review w/ Piping Mngr | Review w/ Project Mngr |  |  | Review w/ Piping & Proj Mngr | Review w/ Project Mngr |  | Review w/ Piping Mngr | Review w/ Project Mngr
[9 empty] | Input to project Document Distribution Matrix | [18 empty] | Develop Control Level Schedule
[8 empty] | Start job planning and Instructions | [12 empty] | Develop SOW |  |  | Develop Estimate | [26 empty] | Prepare Piping Home Office Final Job Report
[8 empty] | Attend all Meetings, Visit Jobsite, Collect Client Specs and keep Piping Manager informed | [6 empty] | Monitor, Control and Report | [5 empty] | Monitor, Control and Report | [6 empty] | Monitor, Control and Report |  |  |  |  | Monitor, Control and Report | [5 empty] | Monitor, Control and Report | [5 empty] | Monitor, Control and Report |  |  |  |  | Monitor, Control and Report |  |  |  | Monitor, Control and Report
Milestones |  |  |  |  | Total Project joint kick-off meeting |  |  |  |  | PFDs and some Design data available |  |  | Process initiates work on P&IDs |  |  | In-house P&ID Review | P&IDs IFA |  |  | P&IDs IFD |  |  | 1 st Vendor Drawings | [10 empty] | Field Move In | Model Review |  | Client Model Review |  |  |  |  | 1st Iso to Shop | 1 st Spools ship to Site |  |  |  | Last Iso to Shop |  |  |  | Last Spools fm Shop
[22 empty] | Util P&IDs | [8 empty] | Vess Orientation Review

## Notes and Instructions
Piping Training - Part - 6
Process Plant Project Secquence Chart, Piping
Notes:
This Piping, Process Plant Project Sequence "Chart" is a broad generalization of the major project activities by the different Piping groups and is not intended to be an absolutely detailed match for every project. It was prepared specifically for use as a guide in this Training Program for Piping Leads.
To use the Chart on screen go to the first page of the Chart, Place the courser in "Cell" C-1 and then go to "Windows (in the tool bar above) and click on "Split" This will freeze the left-hand "B" column. Then you can scroll right to any page and you will still see the discipline designations in the "B" column. On print-Out Column "B" will be repeted on each page.
The major Piping Engineering and Design sub-groups stretch across the pages horizontally. Their individual activities and tasks remain in their individual horizontal bar. Joint activities are shown grouped vertically.
The vertical fields are not intended nor should they be interpretive as implying any unit of time such as Hours, Days, Weeks, Months or Years. They are only there for the presentation of the data.
Instructions:
These "Notes and Instructions" along with the attached "Chart" are "Locked" and Password protected. To make any changes you must "Unlock" the individual document first. After the changes have been completed you should relock the document. The "password" for both documents is located in "Cell" CO-1 of the Chart file.