## Notes and Instructions
Process Plant Project Secquence Chart
Notes:
The Process Plant Project Sequence "Chart" is a broad generalization of the major project activities by the different groups and is not intended to be an absolutely detailed match for every project. It was prepared specifically for use as a guide in this Training Program for Piping Leads.
To use the Chart on screen go to the first page of the Chart, Place the courser in "Cell" C-1 and then go to "Windows (in the tool bar above) and click on "Split" This will freeze the left-hand "B" column. Then you can scroll right to any page and you will still see the discipline designations in the "B" column. On print-Out Column "B" will be repeted on each page.
The major Engineering and Design disciplines stretch across the pages horizontally. Their individual activities and tasks remain in their individual horizontal bar. Joint activities are shown grouped vertically.
The vertical fields are not intended nor should they be interpretive as implying any unit of time such as Hours, Days, Weeks, Months or Years. They are only there for the presentation of the data.
Instructions:
These "Notes and Instructions" along with the attached "Chart" are "Locked" and Password protected. To make any changes you must "Unlock" the individual document first. After the changes have been completed you should relock the document. The "password" for both documents is located in "Cell" CO-1 of the Chart file.

## Chart
jop
PROJECT KICKOFF | [5 empty] | 1 | Preliminary Engineering | [5 empty] | 2 | Preliminary Engineering | [6 empty] | 3 | Scope, Estimate & Schedule |  |  |  |  | 4 | Detailed Engineering and Design | [5 empty] | 5 | Detailed Engineering and Design |  |  |  | 6 | Production Engineering |  | 7 | Project Completion (Home Office) |  |  | 8 | Fabrication & Delivery |  |  | 9 | Construction |  |  | 10
CLIENT | Client and Company PM jointly set time, place and agenda for Kickoff meeting |  |  |  | Joint Kickoff meeting with all Leads in attendance. Agenda includes such key issues as Project Purpose, Goals and Target Completion Date. Other items should include: -Project Execution plan (EPC , EPCM or other.) - Design Execution Plan - Manual, 2D or 3D - Procurement plan, Construction Plan: Stick Build or Module, Direct Hire or Sub-Contract. Client provides all relative documents such as process Block Flow Diagram, information on feed stock, and end products. |  |  |  | Approves PFDs | [9 empty] | Approves P&IDs |  |  | Approves Plot Plan | Review and App. SOW |  | Review and App. Est. |  |  |  | App. Project Go Ahead |  |  |  | Review/app vessels |  | As work progresses, conduct periodic reviews as required |  |  | Hold Client Model Review |  | As work progresses, conduct periodic reviews as required |  |  | As work progresses, conduct periodic reviews as required |  |  |  |  | As work progresses, conduct periodic reviews as required |  |  | As work progresses, conduct periodic reviews as required |  | Finalize Start-up and Operator training
Project Mngmt. |  |  |  | Arrange for project number and space, office & computers | [17 empty] | Each entity or Group drafts a Scope Of Work (SOW) for his/her Discipline. The SOW shall consist of 4 sections; Scope of Facilities (SOF), Scope Of Services (SOS), A Schedule of Deliverables and a List of Assumptions and Exceptions. This Document should be reviewed and approved first by the individual Discipline Department Head and then the Project Engineering Manager and the Project Management. The Project Manager may use all or part to develop the formal Project SOW for submittal to the Client. |  | Each entity or Group develops a detailed Labor Hour Estimate based on the SOW. Each Discipline Estimate should be reviewed and approved by the Discipline Department Head before submittal to Project Management. Project Management shall not make any changes (reductions or additions) to any discipline estimate without the Approval of the Discipline Lead and a corresponding change in the SOW. The Project Manager shall submit a Total Project Estimate to the Client. |  | Each entity or Group develops a detailed Activity and Task Schedule based on the SOW and Labor Hour Estimate. Each Discipline Schedule shall be Activity and Time compatible with all other Discipline Schedules. Each Discipline Schedule should be reviewed and approved by the Discipline Department Head before submittal to Project Management. Project Management shall not make any changes to any discipline Schedule without the Approval of the Discipline Lead The Project Manager shall submit a Total Project Schedule to the Client. |  | Formalize and submit Project Scope, Estimate, Schedule to Client |  | Initiate reporting by Disciplines for Progress, Budget, Schedule |  |  |  |  | Continue reporting by Disciplines for Progress, Budget, Schedule | [5 empty] | Continue reporting by Disciplines for Progress, Budget, Schedule |  | Continue reporting by Disciplines for Progress, Budget, Schedule |  | Produce Project Final Eng. Job Report for Company & Client |  |  | Continue reporting by Disciplines for Progress, Budget, Schedule |  |  | Weekly Construction Status, Progress, Budget, Schedule |  | Prepare for Care, Custody and Control turn-over
[30 empty] | Initiate reporting to Company Management for Progress, Budget, Schedule |  |  |  |  | Continue reporting to Company Management for Progress, Budget, Schedule | [5 empty] | Continue reporting to Company Management for Progress, Budget, Schedule |  | Continue reporting to Company Management for Progress, Budget, Schedule |  |  |  |  | Continue reporting to Company Management for Progress, Budget, Schedule |  |  | Report Construction Status to Company Management
[30 empty] | Initiate reporting to Client for Progress, Budget, Schedule |  |  |  |  | Continue reporting to Client for Progress, Budget, Schedule | [5 empty] | Continue reporting to Client for Progress, Budget, Schedule |  | Continue reporting to Client for Progress, Budget, Schedule |  |  |  |  | Continue reporting to Client for Progress, Budget, Schedule |  |  | Report Construction Status to Client
En'g Mngmt |  | Eng. Mngr selected | [11 empty] | With input form the Client & all disciplined determine the project execution Plan (2D, 3D, or Manual) | [13 empty] | Manage and Control Engineering and Design | [7 empty] | Hold in-house reviews as indiv'l areas are compl't.
[7 empty] | Establish communication methods and channels for all project personnel and purposes | [7 empty] | Establish Document control System and Group to handle Project Documents. | [12 empty] | Establish Controls and Manage Client Change Orders affecting Engineering and Design | [23 empty] | When appropriate de-staff
[8 empty] | Establish Project Reporting methods and Timing. | [19 empty] | Manage and Control Receiving, Routing and Return of Vendor Drawings and Data | [20 empty] | Prepare Home Office (H. O.) Job Report
Process Group |  |  | Process Lead Assigned |  |  |  | Process Engineering receives all relevant process data from the Client and after a period of study starts PFDs (Process Flow Diagrams) |  |  | Develops Mat'l Summ. And Line & Flow data |  | Process initiates development of P&IDs (Piping and Instrument Diagrams) |  |  | Company (in-house) P&ID Reviews attended by all disciplines |  | P&IDS updated for In-house comments | Issue P&IDs to Client For Approval (IFA) | Review Plot Plan Return Comments to Piping | Resolve all Client comments, update P&IDs | Issue P&IDs Approved for Design (AFD) |  | Develop all Utility distribution Diagrams | [20 empty] | All groups prepare Final Job Report covering Scope, Budget, Schedule, Lessons learned & other important issues. Review with Dep't Head and turn in to Eng. Mngr. |  | All personnel released. Discipline Leads should be available on an 'As Needed" basis for questions.
[28 empty] | Develop Operating Instruction: Start-up, Shut-Down and Upset Conditions | [11 empty] | Prepare all Discipline Final Drawings for Issue.
[47 empty] | When appropriate de-staff last personnel |  |  |  |  | When appropriate de-staff supervision
[40 empty] | Develop Discipline De-Staffing Plan |  |  | Follow Discipline De-Staffing Plan | [5 empty] | Prepare Discipline Final H. O. Job Report
Civil Group |  |  | Civil Lead Assigned |  |  |  |  | Civil & Structural start Property Survey and Geotechnical study to determine issues such as Soil conditions to Storm water drainage and disposal |  |  |  | Completes and issue the results of the Site Survey to all project disciplines. |  |  | Work with Piping on Plot Plan developm't issues |  |  |  | Review Plot Plan Return Comments to Piping |  |  |  | Perform MTO of all Bulk Civil Items |  |  |  |  | Based on Approved Plot Plan develop Site Prep drawings for issue to Construction. Include Primary Roads, site fence and other as Req'd
[16 empty] | Develop Specifications for: Roads, Ditches, Berms, Storm Drains, Paving, etc. | [14 empty] | Engineering and Design Development as required. |  |  |  | Engineering and Design Development as required. |  |  |  |  | Prepare all Discipline Final Drawings for Issue.
[47 empty] | When appropriate de-staff last personnel |  |  |  |  | When appropriate de-staff Supervision
[40 empty] | Develop Discipline De-Staffing Plan |  |  | Follow Discipline De-Staffing Plan | [5 empty] | Prepare Discipline Final H. O. Job Report
Structural Group |  |  | Struct. Lead Assigned | [11 empty] | Work with Piping on Plot Plan developm't issues |  |  |  | Review Plot Plan Return Comments to Piping |  |  |  | Perform MTO of all Bulk Struct. Items |  | Input Req'd Data for Computer Design |  |  | Based on Soils Report & Plot Plan develop foundation for equipment as Vendor drawings come in.
[16 empty] | Develop Specifications for Structures (steel/Conc.) Anchor Bolts, Ladders, Platforms, etc. | [14 empty] | Engineering and Design Development as required. |  |  |  | Engineering and Design Development as required. |  |  |  |  | Prepare all Discipline Final Drawings for Issue.
[47 empty] | When appropriate de-staff last personnel |  |  |  |  | When appropriate de-staff supervision
[40 empty] | Develop Discipline De-Staffing Plan |  |  | Follow Discipline De-Staffing Plan | [5 empty] | Prepare Discipline Final H. O. Job Report
Mech. Equip. Group |  |  | Mech. Eqp. Lead Assigned | [5 empty] | Mechanical Equip. starts Project Equipment list with data on type and size |  | Pumps |  |  |  | Work with Piping on Plot Plan developm't issues |  |  |  | Review Plot Plan Return Comments to Piping |  |  |  | Receive & distribute vendor quote eqp. Dwgs
[11 empty] | Exchangers |  |  |  |  | Develop Specifications & Data Sheets for all known equip. |  |  |  | Prepare and Issue Request for Quote (RFQ) for all Equip. | [7 empty] | Continue processing Vendor Drawings and Data as they come in. | [6 empty] | Engineering and Design Development as required. |  |  |  |  | Insure that All In-house and All Vendor Drawings and Data have been Issued.
[11 empty] | Heaters | [35 empty] | When appropriate de-staff last personnel |  |  |  |  | When appropriate de-staff Supervision
Compressors
[11 empty] | Other | [28 empty] | Develop Discipline De-Staffing Plan |  |  | Follow Discipline De-Staffing Plan
Vessels Group |  |  | Vessels Lead Assigned | [7 empty] | Vessels initiates preliminary Vessel and Tank drawings with sizes and Nozzle schedule |  |  |  | Work with Piping on Plot Plan developm't issues |  |  |  | Review Plot Plan Return Comments to Piping |  |  |  | Receive & distribute vendor quote Vess. Dwgs |  | Input Req'd Data for Computer Design | [7 empty] | Update all vessel Drawings and send finals to vessel vendor Approved for Fabrication.
[16 empty] | Develop Specifications & Data Sheets for all known Tanks & Vessels. |  |  |  | Prepare and Issue Request for Quote (RFQ) for all Vessels & Tanks | [7 empty] | Engineering and Design Development as required. | [6 empty] | Engineering and Design Development as required. |  |  |  |  | Insure that All In-house and All Vendor Drawings and Data have been Issued.
[47 empty] | When appropriate de-staff last personnel |  |  |  |  | When appropriate de-staff supervision
[40 empty] | Develop Discipline De-Staffing Plan |  |  | Follow Discipline De-Staffing Plan | [5 empty] | Prepare Discipline Final H. O. Job Report
Piping Group |  |  | Piping Lead Assigned | [7 empty] | Piping Mat'l Eng (PME) starts Line Class Specs |  |  | Piping design starts Plot Plan Study |  |  |  | Receive IFA P&IDs and update Plot Plan | Issue Prelim. Plot Plan for In-house review | Resolve all in-house Plot Plan comments & update | Issue Plot Plan to Client for Approval |  | Perform 1st MTO of all Bulk Piping for RFQ & Est. |  | Input Req'd Data for Computer Design |  |  | Develop detailed Vessel orientation model/drawings complete with all nozzle locations, pipe, pipe supports, pipe guides, ladders & platforms |  |  |  | Joint Vess. Orient. Review w/ Process & Vessels | Initiate detailed design of all piping areas complete with Structures, Pumps, Exchangers, Compressors, Heaters, Pipe Racks and Piping. |  | Continue detailed design of all piping areas complete with Structures, Pumps, Exchangers, Compressors, Heaters, Pipe Racks and Piping. |  | Update 3D Models as required |  | Update 3D Models as required | Extract Secondary MTO for "Purchase" |  |  | After all Isometrics are issued download Final MTO and check for shortages and overages. Take action to buy the Shortages. In conversation with Construction & the Client determine what action to take on Overages.
[14 empty] | PME starts Prelim. Line List | [32 empty] | The Project may elect to assign a Piper to the Pipe Fabrication Shop(s) to monitor progress and resolve questions. The hours and costs should be included in the Project management budget. |  |  |  | The Project may elect to assign a Piper to the Jobsite to resolve problems and answer questions.
Extract Piping Isometrics and perform Detailed Quality Control Check, Corrections, Model update prior to Issue. Completed Isometrics are then Issued in accordance with Project Procedures.
[28 empty] | Pipe Stress review & analyze piping as Req'd | [18 empty] | When appropriate de-staff last personnel |  |  |  |  | When appropriate de-staff supervision
[14 empty] | Piping Eng. Lead starts Scope Planning | [13 empty] | Establish 3D Design Partition areas | [14 empty] | Develop & follow Discipline De-Staffing Plan | [5 empty] | Prepare Discipline Final H. O. Job Report
Electrical Group |  |  | Elect. Lead Assigned | [7 empty] | Electrical starts Motor List, and other activities relating to Power, Lighting & Communications |  |  |  | Work with Piping on Plot Plan developm't issues |  |  |  | Review Plot Plan Return Comments to Piping |  |  |  | Perform MTO of all Bulk Elect. Items |  | Input Req'd Data for Computer Design
[16 empty] | Develop Specifications & Data Sheets for all known equip. |  |  |  | Prepare and Issue Request for Quote (RFQ) for all Elect. Equip. | [7 empty] | Develop underground cable routing/Duct Banks. Coordinate all underground work with Piping, Structural, Civil and Instruments. Coordinate all work with the Design Model | [6 empty] | Engineering and Design Development as required. |  |  |  |  | Prepare all Discipline Final Drawings for Issue.
[47 empty] | When appropriate de-staff last personnel |  |  |  |  | When appropriate de-staff supervision
[40 empty] | Develop Discipline De-Staffing Plan |  |  | Follow Discipline De-Staffing Plan | [5 empty] | Prepare Discipline Final H. O. Job Report
Instrument Group |  |  | Instru. Lead Assigned | [10 empty] | Instruments starts Instru. List, and other activities relating to Cable Tray runs & local control panels |  | Work with Piping on Plot Plan developm't issues |  |  | Review Plot Plan Return Comments to Piping |  |  |  | Perform MTO of all Bulk Instru. Items |  | Input Req'd Data for Computer Design
[20 empty] | Develop Spec & Data Sht for all known Instru. | [7 empty] | Develop individual Instrument connection Details, Loop Detail Drawings & Cable Tray sizes and routing. Coordinate all work with Piping and the Design Model | [6 empty] | Engineering and Design Development as required. |  |  |  |  | Prepare all Discipline Final Drawings for Issue.
[47 empty] | When appropriate de-staff last personnel |  |  |  |  | When appropriate de-staff Supervision
[40 empty] | Develop Discipline De-Staffing Plan |  |  | Follow Discipline De-Staffing Plan | [5 empty] | Prepare Discipline Final H. O. Job Report
Notes: